## Working Data
Project ID | Drive Time | Tilt | Azimuth | Panel QTY | System Rating (kW DC) | Inverter Manufacturer | Array Type | Squirrel Screen | Consumption Monitoring | Truss / Rafter | Reinforce- ments | Rough Electrical Inspection | Interconnection Type | Module Length | Module Width | Module Weight | # of Arrays | # of reinforcement | Roof Type | Attachment Type | Portrait / Landscape | # of Stories | Install Season | Total Direct Time for Project for Hourly Employees (Including Drive Time) | Total # of Days on Site | Total # Hourly Empoyees on Site | Estimated # of Salaried Employees on Site | Estimated Salary Hours | Estimated Total Direct Time | Estimated Total # of People on Site | Notes
001 | 21 mins | 33° | 180° | 19 | 6.84 | SolarEdge | Roof Mount | Yes |  | Truss | No | No | A1 | 67.8 | 40 | 43 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Spring | 19:00 | 1 | 2 | 2 | 19:00 | 38:00 | 4
002 | 23 mins | 45° | 139° | 18 | 6.57 | SolarEdge | Roof Mount | Yes |  | Rafter | Yes | Yes | A1 | 67.8 | 40 | 43 | 1 | 2 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Spring | 33:30 | 2 | 2 | 2 | 33:30 | 67:00 | 4
003 | 21 mins | 24° | 180° | 16 | 5.12 | SolarEdge | Roof Mount | No |  | Truss | No | No | A3 | 66.3 | 39.4 | 41.2 | 2 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Spring | 25:20 | 2 | 2 | 2 | 25:20 | 50:40 | 4
004 | 38 mins | 20° | 104° | 27 | 10.8 | Enphase | Roof Mount | No |  | Truss | No | No | C2 | 79.3 | 39.4 | 51.8 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Spring | 27:00 | 2 | 2 | 2 | 27:00 | 54:00 | 4 | Yes this job and the one below it both happened
005 | 38 mins | 20° | 180° | 27 | 10.8 | Enphase | Roof Mount | No |  | Truss | No | No | C2 | 79.3 | 39.4 | 51.8 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Both | 1 | Spring | 27:00 | 2 | 2 | 2 | 27:00 | 54:00 | 4 | Yes this job and the one above it both happened
006 | 45 mins | 18.4° | 180° | 18 | 6.12 | SolarEdge | Roof Mount | No |  | Truss | No | No | A1 | 68.5 | 40.5 | 43.9 | 1 | 0 | Asphalt Shingles | Unknown | Portrait | 1 | Spring | 17:00 | 1 | 2 | 2 | 17:00 | 34:00 | 4
007 | 24 mins | 26° | 200° | 13 | 4.225 | SolarEdge | Roof Mount | Yes |  | Truss | No | Yes | A3 | 65.43 | 39.45 | 41.6 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Spring | 19:30 | 1 | 2 | 2 | 19:30 | 39:00 | 4
008 | 21 mins | 10° | 205° | 20 | 7.3 | SolarEdge | Roof Mount | No |  | Rafter | No | Yes | B2 | 67.8 | 40 | 43 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Spring | 38:15 | 3 | 2 | 2 | 38:15 | 76:30 | 4
009 | 30 mins | 18° | 185° | 18 | 5.76 | SolarEdge | Roof Mount | No |  | Truss | No | No | A2 | 65.94 | 39.25 | 39.7 | 1 | 0 | Asphalt Shingles | Unknown | Portrait | 2 | Spring | 25:45 | 2 | 2 | 2 | 25:45 | 51:30 | 4
010 | 6 mins | 31° | 90° | 16 | 5.12 | SolarEdge | Roof Mount | Yes |  | Rafter | Yes | Yes | B2 | 65.94 | 39.25 | 39.7 | 1 | 10 | Asphalt Shingles | Flashfoot 2 | Landscape | 1 | Spring | 33:45 | 2 | 2 | 2 | 33:45 | 67:30 | 4
011 | 16 mins | 26.6° | 130° | 22 | 8.03 | Enphase | Roof Mount | Yes |  | Truss | No | No | A1 | 67.8 | 40 | 43 | 2 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Spring | 43:30 | 4 | 2 | 2 | 43:30 | 87:00 | 4
012 | 51 mins | 45° | 180° | 24 | 8.52 | Enphase | Roof Mount | No |  | Truss | No | No | C* | 67.8 | 40 | 43 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Spring | 12:45 | 1 | 1 | 2 | 25:30 | 38:15 | 3
013 | 10 mins | 45° | 215° | 20 | 7.3 | SolarEdge | Roof Mount | No |  | Rafter | No | No | C* | 67.8 | 40 | 43 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Spring | 37:30 | 2 | 2 | 2 | 37:30 | 75:00 | 4
014 | 36 mins | 35°/27° | 230°/140° | 31 | 11.005 | SolarEdge | Roof Mount | No |  | Truss | No | No | C3 | 67.8 | 40 | 43 | 5 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Spring | 35:30 | 3 | 2 | 2 | 35:30 | 71:00 | 4
015 | 9 mins | 24° | 180° | 32 | 11.36 | Enphase | Roof Mount | No |  | Truss | No | Yes | C1 | 67.8 | 40 | 43 | 3 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Spring | 40:30 | 3 | 3 | 2 | 27:00 | 67:30 | 5
016 | 30 mins | 32° | 218° | 23 | 7.59 | SolarEdge | Roof Mount | No |  | Truss | No | No | A2 | 66.53 | 39.21 | 39.7 | 2 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Spring | 29:30 | 2 | 2 | 2 | 29:30 | 59:00 | 4
017 | 21 mins | 24° | 180° | 20 | 6.4 | SolarEdge | Roof Mount | No |  | Truss | No | No | A1 | 39.4 | 66.9 | 41 | 2 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Spring | 20:00 | 1 | 2 | 2 | 20:00 | 40:00 | 4
018 | 25 mins | 14° | 170° | 12 | 4.26 | SolarEdge | Roof Mount | Yes |  | Rafter | No | Yes | B2 | 66.93 | 40 | 39.7 | 1 | 0 | Standing Seam Metal Roof | S-5! | Portrait | 1 | Summer | 24:15 | 2 | 2 | 2 | 24:15 | 48:30 | 4
019 | 7 mins | 36° | 180° | 14 | 5.18 | Enphase | Roof Mount | Yes |  | Truss | No | Yes | A3 | 70.67 | 39.98 | 41.9 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Spring | 33:30 | 2 | 2 | 2 | 33:30 | 67:00 | 4
020 | 49 mins | 10°/18° | 190° | 43 | 18.275 | SolarEdge | Roof Mount | No |  | Purlin | Yes | No | A1 | 81.9 | 40.6 | 55.1 | 1 | 2 | Ag Metal | Ejot | Landscape | 1 | Summer | 82:15 | 4 | 3 | 2 | 54:50 | 137:05 | 5
021 | 44 mins | 18° | 180° | 14 | 5.95 | SolarEdge | Roof Mount | No |  | Rafter | No | No | B* | 81.9 | 40.6 | 55.1 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Summer | 25:00 | 1 | 3 | 2 | 16:40 | 41:40 | 5
022 | 11 mins | 10°/38° | 235° | 20 | 7.4 | Enphase | Roof Mount | Yes |  | Rafter | No | Yes | C1 | 70.67 | 39.98 | 41.9 | 3 | 0 | EPDM (Flat Roof) | Flashloc RM | Both | 2 | Summer | 33:30 | 2 | 3 | 2 | 22:20 | 55:50 | 5
023 | 44 mins | 18° | 180° | 49 | 21.07 | SolarEdge | Roof Mount | No |  | Purlin | No | No | A* | 81.89 | 40.56 | 55.11 | 1 | 0 | Ag Metal | Ejot | Landscape | 1 | Summer | 116:45 | 7 | 3 | 2 | 77:50 | 194:35 | 5
024 | 40 mins | 26° | 108° | 28 | 10.36 | SolarEdge | Roof Mount | No |  | Truss | No | No | C* | 70.67 | 39.98 | 41.9 | 2 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Summer | 10:00 | 1 | 1 | 2 | 20:00 | 30:00 | 3
025 | 17 mins | 18°/21° | 185° | 24 | 8.76 | Enphase | Roof Mount | No |  | Truss | No | No | A2 | 67.8 | 40 | 43 | 2 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Spring | 32:00 | 2 | 2 | 2 | 32:00 | 64:00 | 4
026 | 29 mins | 16°/16° | 178°/267° | 12 | 4.44 | Enphase | Roof Mount | Yes |  | Rafter | No | No | B1 | 70.67 | 39.98 | 41.9 | 2 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Fall | 13:30 | 1 | 2 | 2 | 13:30 | 27:00 | 4
027 | 28 mins | 20° |  | 14 | 4.9 | SMA | Roof Mount | No |  | Truss | No | Yes | A1 | 69.44 | 41.26 | 46.5 | 2 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Summer | 31:15 | 2 | 3 | 2 | 20:50 | 52:05 | 5
028 | 25 mins | 24° | 180° | 22 | 7.81 | Enphase | Roof Mount | Yes |  | Truss | No | Yes | A2 | 68.5 | 41 | 41 | 3 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Summer | 39:00 | 3 | 2 | 2 | 39:00 | 78:00 | 4
029 | 4 mins | 25° | 165° | 11 | 4.07 | SolarEdge | Roof Mount | No |  | Truss | No | Yes | A1 | 70.67 | 39.98 | 41.9 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Summer | 23:45 | 2 | 2 | 2 | 23:45 | 47:30 | 4
030 | 16 mins | 18° | 180° | 13 | 4.29 | Enphase | Roof Mount | No |  | Truss | No | No | A1 | 66.9 | 39.4 | 41 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Summer | 17:30 | 2 | 2 | 3 | 26:15 | 43:45 | 5
031 | 26 mins | 34° | 260° | 15 | 5.1 | SolarEdge | Roof Mount | No |  | Truss | No | No | A1 | 68.5 | 40.5 | 43.9 | 2 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Summer | 24:55 | 1 | 3 | 3 | 24:55 | 49:50 | 6
032 | 12 mins | 19° | 177°/260° | 16 | 5.92 | Enphase | Roof Mount | No |  | Truss | No | No | A1 | 70.67 | 39.98 | 41.9 | 2 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Summer | 26:10 | 1 | 3 | 3 | 26:10 | 52:20 | 6
033 | 13 mins | 18° | 200° | 11 | 4.07 | SolarEdge | Roof Mount | Yes |  | Rafter | Yes | No | B2 | 70.67 | 39.98 | 41.9 | 1 | 18 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Summer | 24:10 | 1 | 3 | 3 | 24:10 | 48:20 | 6
034 | 42 mins | 30° | 180° | 13 | 4.81 | SolarEdge | Roof Mount | No |  | Rafter | Yes | No | C2 | 70.67 | 39.98 | 41.9 | 1 | 11 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Summer | 29:10 | 1 | 3 | 3 | 29:10 | 58:20 | 6
035 | 15 mins | 25° | 270° | 23 | 7.59 | SolarEdge | Roof Mount | No |  | Truss | No | No | A1 | 66.53 | 39.21 | 39.7 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Summer | 26:45 | 1 | 3 | 3 | 26:45 | 53:30 | 6
036 | 21 mins | 30° | 180° | 13 | 4.81 | Enphase | Roof Mount | Yes |  | Truss | No | Yes | A1 | 70.67 | 39.98 | 41.9 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Summer | 25:15 | 1 | 3 | 3 | 25:15 | 50:30 | 6
037 | 26 mins | 38° | 173° | 9 | 4.05 | Enphase | Roof Mount | No |  | Rafter | No | Yes | A3 | 83.07 | 41 | 50.71 | 1 | 0 | Standing Seam Metal Roof | S-5! | Landscape | 1 | Fall | 71:00 | 3 | 3 | 3 | 71:00 | 142:00 | 6
038 | 15 mins | 16° | 192° | 29 | 10.73 | Enphase | Roof Mount | Yes |  | Truss | No | Yes | C1 | 70.67 | 39.98 | 41.9 | 2 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Summer | 37:57 | 2 | 3 | 3 | 37:57 | 75:54 | 6
039 | 25 mins | 18° | 157° | 16 | 6.08 | SolarEdge | Roof Mount | No |  | Rafter | No | Yes | B2 | 72.4 | 40.6 | 43 | 2 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Summer | 28:22 | 1 | 3 | 3 | 28:22 | 56:44 | 6
040 | 22 mins |  | 148°/240° | 43 | 15.695 | Enphase | Roof Mount | No |  | Truss | No | No | C1 | 67.8 | 40 | 43 | 8 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Summer | 76:15 | 3 | 3 | 3 | 76:15 | 152:30 | 6
041 | 36 mins | 30° | 260° | 36 | 13.32 | SolarEdge | Roof Mount | No |  | Truss | No | No | C* | 70.67 | 39.98 | 41.9 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Summer | 54:54 | 3 | 3 | 3 | 54:54 | 109:48 | 6
042 | 25 mins | 10° | 162° | 16 | 5.28 | SolarEdge | Roof Mount | No |  | Truss | No | Yes | B2 | 66.9 | 39.4 | 41 | 1 | 0 | Standing Seam Metal Roof | S-5! | Portrait | 1 | Summer | 17:30 | 1 | 2 | 3 | 26:15 | 43:45 | 5
044 | 22 mins | 20°/37° | 215°/125° | 21 | 7.77 | Enphase | Roof Mount | Yes |  | Truss | No | No | A1 | 70.67 | 39.98 | 41.9 | 3 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Fall | 23:45 | 2 | 3 | 3 | 23:45 | 47:30 | 6
045 | 10 mins | 23° | 135° | 9 | 3.33 | Enphase | Roof Mount | Yes |  | Rafter | Yes | Yes | B2 | 70.67 | 39.98 | 41.9 | 1 | 11 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Summer | 33:10 | 2 | 3 | 3 | 33:10 | 66:20 | 6
046 | 16 mins | 30° | 180° | 54 | 23.22 | Enphase | Ground Mount | No |  | Grount Mount | No | No | C2 | 81.89 | 40.56 | 55.11 | 2 | 0 | Ground Mount | Ground Mount | Portrait | 0 | Fall | 104:40 | 8 | 3 | 3 | 104:40 | 209:20 | 6
047 | 18 mins | 28° | 200° | 14 | 5.18 | SolarEdge | Roof Mount | Yes |  | Truss | No | No | A1 | 70.67 | 39.98 | 41.9 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Fall | 13:30 | 2 | 1 | 3 | 40:30 | 54:00 | 4
049 | 43 mins | 25° | 180° | 20 | 7.4 | Enphase | Roof Mount | No |  | Truss | No | No | A3 | 70.67 | 39.98 | 41.9 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Fall | 41:30 | 3 | 2 | 3 | 62:15 | 103:45 | 5
050 | 56 mins | 30° | 180° | 48 | 17.76 | SolarEdge | Ground Mount | No |  | Grount Mount | No | No | C* | 70.67 | 39.98 | 41.9 | 2 | 0 | Ground Mount | Ground Mount | Portrait | 0 | Fall | 129:00 | 7 | 3 | 3 | 129:00 | 258:00 | 6
051 | 27 mins | 24° | 180°/90° | 19 | 7.03 | Enphase | Roof Mount | No |  | Truss | No | Yes | A2 | 70.67 | 39.98 | 41.9 | 2 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Fall | 24:30 | 1 | 3 | 3 | 24:30 | 49:00 | 6
052 | 16 mins | 24° | 185° | 31 | 11.625 | SolarEdge | Roof Mount | No |  | Truss | No | No | A1 | 67.8 | 40 | 43 | 3 | 0 | Asphalt Shingles | Flashfoot 2 | Both | 2 | Fall | 19:39 | 1 | 2 | 3 | 29:28 | 49:08 | 5
054 | 25 mins | 20° | 175° | 12 | 4.38 | Enphase | Roof Mount | Yes |  | Truss | No | Yes | A1 | 67.8 | 40 | 43 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Fall | 16:40 | 1 | 2 | 3 | 25:00 | 41:40 | 5
055 | 42 mins | 22° | 180° | 14 | 4.97 | Enphase | Roof Mount | Yes |  | Truss | No | No | C2 | 67.8 | 40 | 43 | 2 | 0 | Asphalt Shingles | Flashfoot 2 | Both | 2 | Fall | 17:10 | 1 | 2 | 3 | 25:45 | 42:55 | 5
056 | 33 mins | 37° | 180° | 14 | 5.18 | SolarEdge | Roof Mount | No |  | Truss | No | No | C* | 70.67 | 39.98 | 41.9 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Fall | 15:30 | 1 | 2 | 3 | 23:15 | 38:45 | 5
057 | 43 mins | 30° | 180° | 28 | 12.6 | SolarEdge | Ground Mount | No |  | Grount Mount | No | No | B1 | 82.79 | 40.94 | 55.12 | 1 | 0 | Ground Mount | Ground Mount | Portrait | 0 | Fall | 64:00 | 3 | 3 | 3 | 64:00 | 128:00 | 6
058 | 12 mins | 32° | 170° | 17 | 6.46 | Enphase | Roof Mount | No |  | Truss | No | Yes | A2 | 70.67 | 39.98 | 41.9 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Fall | 23:15 | 1 | 3 | 3 | 23:15 | 46:30 | 6
060 | 12 mins | 24° | 135° | 16 | 5.92 | Enphase | Roof Mount | Yes |  | Truss | No | No | A1 | 70.67 | 39.98 | 41.9 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Fall | 22:30 | 1 | 3 | 3 | 22:30 | 45:00 | 6
061 | 22 mins | 38° | 180° | 18 | 6.66 | Enphase | Roof Mount | No |  | Rafter | Yes | Yes | B2 | 70.67 | 39.98 | 41.9 | 1 | 22 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Fall | 30:45 | 1 | 3 | 3 | 30:45 | 61:30 | 6
062 | 37 mins | 20° | 245° | 21 | 7.77 | SolarEdge | Roof Mount | No |  | Truss | No | No | A1 | 70.67 | 39.98 | 41.9 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Winter | 23:15 | 2 | 3 | 3 | 23:15 | 46:30 | 6
063 | 23 mins |  |  | 22 | 8.03 | SolarEdge | Roof Mount | Yes |  | Rafter | Yes | Yes | A1 | 67.8 | 40 | 43 | 1 | 14 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Fall | 30:30 | 2 | 2 | 3 | 45:45 | 76:15 | 5
064 | 22 mins | 30° | 230° | 16 | 6.08 | SolarEdge | Roof Mount | Yes |  | Rafter | Yes | Yes | A1 | 70.67 | 39.98 | 41.9 | 2 | 2 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Fall | 27:40 | 2 | 2 | 3 | 41:30 | 69:10 | 5
065 | 26 mins | 18° | 270° | 13 | 4.81 | Enphase | Roof Mount | No |  | Truss | No | Yes | A2 | 70.67 | 39.98 | 41.9 | 1 | 0 | Asphalt Shingles | Unknown | Portrait | 2 | Fall | 30:30 | 2 | 3 | 3 | 30:30 | 61:00 | 6
066 | 24 mins | 30° | 135° | 19 | 7.03 | Enphase | Roof Mount | No |  | Truss | No | Yes | A1 | 67.8 | 40 | 43 | 4 | 0 | Asphalt Shingles | Flashfoot 2 | Both | 2 | Fall | 27:00 | 1 | 3 | 3 | 27:00 | 54:00 | 6
067 | 40 mins | 31° | 180° | 20 | 7.6 | Enphase | Roof Mount | No |  | Truss | No | No | A1 | 68.5 | 41.02 | 40.8 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Fall | 25:30 | 1 | 3 | 3 | 25:30 | 51:00 | 6
068 | 24 mins | 16° | 180° | 12 | 4.38 | Enphase | Roof Mount | Yes |  | Rafter | Yes | No | A1 | 69.37 | 40.91 | 44.09 | 1 | 7 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Winter | 29:25 | 2 | 3 | 3 | 29:25 | 58:50 | 6
069 | 27 mins | 22.6° | 90°/180°/270° | 21 | 7.77 | Enphase | Roof Mount | No |  | Truss | No | Yes | A1 | 70.67 | 39.98 | 41.9 | 4 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Fall | 27:00 | 2 | 3 | 3 | 27:00 | 54:00 | 6 | Installed a car charger
070 | 32 mins | 18° | 180° | 36 | 13.32 | Enphase | Roof Mount | No |  | Truss | No | No | A1 | 70.67 | 39.98 | 41.9 | 1 | 0 | Ag Metal | Ejot | Landscape | 2 | Winter | 56:15 | 3 | 3 | 3 | 56:15 | 112:30 | 6
071 | 30 mins | 21° | 180° | 17 | 5.61 | SolarEdge | Roof Mount | No |  | Truss | No | No | A1 | 66.53 | 39.21 | 39.7 | 2 | 0 | Asphalt Shingles | Flashfoot 2 | Both | 2 | Fall | 23:25 | 2 | 3 | 3 | 23:25 | 46:50 | 6
072 | 14 mins | 26° | 200° | 16 | 5.52 | SolarEdge | Roof Mount | Yes |  | Truss | No | Yes | A1 | 68.8 | 41.5 | 44.8 | 2 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Fall | 33:00 | 3 | 3 | 3 | 33:00 | 66:00 | 6
073 | 26 mins | 32° | 180° | 14 | 5.32 | Enphase | Roof Mount | No |  | Truss | No | No | A1 | 70.67 | 39.98 | 41.9 | 1 | 0 | Asphalt Shingles | Unknown | Portrait | 1 | Fall | 24:30 | 1 | 3 | 3 | 24:30 | 49:00 | 6
074 | 15 mins | 22.6° | 180° | 19 | 7.22 | SolarEdge | Roof Mount | Yes |  | Truss | No | No | A2 | 70.67 | 39.98 | 41.9 | 1 | 0 | Asphalt Shingles | Unknown | Portrait | 1 | Winter | 20:15 | 1 | 3 | 3 | 20:15 | 40:30 | 6
075 | 3 mins | 24° | 200° | 4 | 1.52 | Enphase | Roof Mount | No |  | Truss | No | Yes | A1 | 70.67 | 39.98 | 41.9 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Winter | 20:45 | 1 | 3 | 1 | 6:55 | 27:40 | 4
076 | 28 mins | 30° | 210° | 36 | 13.32 | Enphase | Roof Mount | Yes |  | Truss | No | Yes | A1 | 67.8 | 40 | 43 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Winter | 39:00 | 2 | 2 | 3 | 58:30 | 97:30 | 5
077 | 39 mins | 30° | 180° | 14 | 5.95 | SolarEdge | Ground Mount | No |  | Grount Mount | No | No | A1 | 81.9 | 40.6 | 55.1 | 1 | 0 | Ground Mount | Ground Mount | Portrait | 0 | Spring | 36:25 | 2 | 3 | 2 | 24:17 | 60:42 | 5
078 | 25 mins |  | 140° | 18 | 6.66 | Enphase | Roof Mount | Yes |  | Truss | No | Yes | B1 | 67.8 | 40 | 43 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Summer | 15:30 | 1 | 2 | 2 | 15:30 | 31:00 | 4
079 | 10 mins | 26° | 260°/80° | 28 | 11.2 | Enphase | Roof Mount | Yes |  | Truss | No | No | B1 | 71.7 | 40 | 45 | 2 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Spring | 35:15 | 2 | 2 | 2 | 35:15 | 70:30 | 4
080 | 27 mins |  |  | 29 | 10.73 | Enphase | Roof Mount | Yes |  | Rafter | No | Yes | A* | 67.8 | 40 | 43 | 4 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Spring | 36:15 | 4 | 2 | 2 | 36:15 | 72:30 | 4
084 | 44 mins | 17° | 180° | 15 | 5.55 | Enphase | Roof Mount | Yes |  | Truss | No | No | A1 | 67.8 | 40 | 43 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Landscape | 1 | Spring | 38:05 | 5 | 3 | 2 | 25:23 | 63:28 | 5 | Time data looks wrong to me
085 | 25 mins | 37° | 155° | 28 | 10.36 | SolarEdge | Roof Mount | Yes |  | TJI | No | Yes | A1 | 67.8 | 40 | 43 | 1 | 0 | Asphalt Shingles | RT Mini | Portrait | 1 | Spring | 22:05 | 2 | 1 | 2 | 44:10 | 66:15 | 3
087 | 7 mins | 18° | 270°/180°/90° | 9 | 3.42 | Enphase | Roof Mount | Yes |  | Rafter | No | Yes | A1 | 70.67 | 39.98 | 41.9 | 3 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Spring | 24:45 | 2 | 2 | 2 | 24:45 | 49:30 | 4
089 | 13 mins | 26.6° | 115° | 24 | 9.12 | Enphase | Roof Mount | Yes |  | Truss | No | Yes | A2 | 70.67 | 39.98 | 41.9 | 2 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Spring | 1:30 | 1 | 1 | 2 | 3:00 | 4:30 | 3 | time data looks wrong to me
090 | 27 mins | 26° | 270°/90° | 11 | 4.07 | SolarEdge | Roof Mount | No |  | Truss | No | Yes | A1 | 69.4 | 40.8 | 43 | 2 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Spring | 14:55 | 2 | 2 | 2 | 14:55 | 29:50 | 4
091 | 25 mins | 14°/18° | 180°/270° | 21 | 7.98 | Enphase | Roof Mount | No |  | Truss | No | No | A3 | 70.67 | 39.98 | 41.9 | 3 | 0 | Asphalt Shingles | Flashfoot 2 | Both | 1 | Spring | 10:30 | 1 | 1 | 2 | 21:00 | 31:30 | 3
092 | 34 mins | 18° | 180° | 10 | 3.7 | SolarEdge | Roof Mount | No |  | Truss | No | No | C* | 69.13 | 40.91 | 45.19 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Spring | 10:00 | 1 | 1 | 2 | 20:00 | 30:00 | 3
093 | 48 mins | 18° | 145° | 14 | 5.6 | Enphase | Roof Mount | No |  | Purlin | No | No | A2 | 71.7 | 40 | 45 | 1 | 0 | Ag Metal | Ejot | Portrait | 2 | Spring | 21:36 | 1 | 3 | 2 | 14:24 | 36:00 | 5
094 | 14 mins | 26° | 180° | 16 | 6.4 | Enphase | Roof Mount | Yes |  | Truss | No | Yes | A1 | 71.7 | 40 | 45 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Spring | 29:55 | 3 | 3 | 2 | 19:57 | 49:52 | 5
095 | 1 hour 32 mins | 18° | 135° | 20 | 9 | SolarEdge | Roof Mount | No |  | Purlin | No | No | A* | 82.79 | 40.94 | 55.12 | 1 | 0 | Ag Metal | Ejot | Landscape | 1 | Spring | 18:30 | 1 | 2 | 2 | 18:30 | 37:00 | 4
096 | 21 mins | 30° | 90°/180°/270° | 56 | 20.72 | SolarEdge | Roof Mount | Yes |  | Truss | No | No | A* | 67.8 | 40 | 43 | 7 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Spring | 43:48 | 5 | 1 | 2 | 87:36 | 131:24 | 3
104 | 21 mins | 30° | 175° | 24 | 8.88 | Enphase | Roof Mount | No |  | Truss | No | No | A1 | 68.5 | 41.01 | 41.02 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Spring | 18:15 | 1 | 2 | 2 | 18:15 | 36:30 | 4
112 | 25 mins | 26° | 170°/260° | 26 | 9.62 | Enphase | Roof Mount | Yes |  | Truss | No | Yes | A2 | 69.13 | 40.91 | 45.19 | 2 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Summer | 3:10 | 1 | 1 | 2 | 6:20 | 9:30 | 3 | Time data looks wrong to me
119 | 29 mins | 24° | 200°/110° | 27 | 10.8 | Enphase | Roof Mount | Yes |  | Truss | No | No | A1 | 71.7 | 40 | 45 | 3 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Summer | 36:25 | 2 | 2 | 2 | 36:25 | 72:50 | 4
160 | 31 mins | 24° | 120°/210° | 37 | 13.69 | Enphase | Roof Mount | No | Yes | Truss | No | No | B1 | 69.4 | 40.8 | 43 | 5 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Spring | 48:00 | 3 | 3 | 1 | 16:00 | 64:00 | 4 | Data from here onwards is much more accurate
161 | 31 mins | 30° | 180° | 14 | 5.6 | Enphase | Roof Mount | Yes | No | Rafter | Yes | No | B2 | 71.7 | 40 | 45 | 1 | 1 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Winter | 14:45 | 2 | 2 | 1 | 7:22 | 22:08 | 3
162 | 22 mins | 25° | 180° | 21 | 8.4 | Enphase | Roof Mount | Yes | Yes | Truss | No | No | A4 | 71.7 | 40 | 45 | 2 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Spring | 36:15 | 2 | 2 | 0 | 0:00 | 36:15 | 2
163 | 23 mins | 22° | 180° | 18 | 7.2 | Enphase | Roof Mount | Yes | Yes | Rafter | Yes | No | B1 | 71.7 | 40 | 45 | 1 | 23 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Winter | 78:40 | 4 | 3 | 1 | 26:13 | 104:53 | 4
164 | 36 mins | 30° | 270° | 18 | 8.1 | SolarEdge | Roof Mount | Yes | No | Rafter | No | No | A* | 82.79 | 40.94 | 55.12 | 4 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Spring | 44:30 | 3 | 3 | 0 | 0:00 | 44:30 | 3
165 | 31 mins | 40° | 170° | 26 | 10.4 | Enphase | Roof Mount | Yes | Yes | Truss | No | No | A1 | 71.7 | 40 | 45 | 3 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Fall | 69:30 | 2 | 4 | 0 | 0:00 | 69:30 | 4 | New construction
166 | 30 mins | 26°/40° | 260°/170° | 24 | 9.36 | SolarEdge | Roof Mount | Yes | No | Truss | No | No | A1 | 69.06 | 43.15 | 46.3 | 3 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Spring | 84:00 | 5 | 4 | 0 | 0:00 | 84:00 | 4 | New construction - lots of trips
167 | 24 mins | 26° | 190° | 17 | 6.63 | SolarEdge | Roof Mount | No | No | Truss | No | No | A1 | 69.06 | 43.15 | 46.3 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Spring | 52:40 | 3 | 3 | 0 | 0:00 | 52:40 | 3
168 | 16 mins | 34° | 205° | 15 | 5.85 | SolarEdge | Roof Mount | No | No | Truss | No | No | A4 | 69.06 | 43.15 | 46.3 | 2 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Spring | 21:15 | 1 | 2 | 0 | 0:00 | 21:15 | 2
169 | 32 mins | 26° | 90° | 26 | 10.4 | Enphase | Roof Mount | Yes | Yes | Truss | No | No | A1 | 71.7 | 40 | 45 | 2 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Winter | 56:30 | 2 | 3 | 1 | 18:50 | 75:20 | 4
170 | 14 mins | 26° | 200° | 20 | 8 | Enphase | Roof Mount | Yes | Yes | Truss | No | No | A1 | 71.7 | 40 | 45 | 2 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Winter | 45:20 | 3 | 3 | 0 | 0:00 | 45:20 | 3
171 | 37 mins | 30° | 180° | 20 | 9.7 | SMA | Ground Mount | No | No | Grount Mount | No | No | A* | 87.2 | 41.1 | 64.2 | 1 | 0 | Ground Mount | Ground Mount | Landscape | 0 | Spring | 83:43 | 2 | 4 | 0 | 0:00 | 83:43 | 4
172 | 19 mins | 19° | 180° | 16 | 6.4 | Enphase | Roof Mount | Yes | No | Rafter | No | No | A1 | 71.7 | 40 | 45 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Summer | 31:35 | 1 | 4 | 0 | 0:00 | 31:35 | 4
173 | 56 mins | 30° | 180° | 48 | 19.2 | SMA | Ground Mount | No | No | Grount Mount | No | No | C* | 74 | 41.1 | 48.5 | 2 | 0 | Ground Mount | Ground Mount | Portrait | 0 | Spring | 141:06 | 4 | 4 | 2 | 70:33 | 211:39 | 6
174 | 36 mins | 30° | 180° | 9 | 4.365 | SolarEdge | Ground Mount | No | No | Grount Mount | No | No | A1 | 87.2 | 41.1 | 64.2 | 1 | 0 | Ground Mount | Ground Mount | Landscape | 0 | Spring | 107:45 | 3 | 4 | 0 | 0:00 | 107:45 | 4
175 | 43 mins | 30° | 190° | 9 | 3.6 | SolarEdge | Roof Mount | Yes | No | Truss | No | No | C* | 71.7 | 40 | 45 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Spring | 28:30 | 1 | 3 | 0 | 0:00 | 28:30 | 3
176 | 42 mins | 26 | 240°/60° | 50 | 24.25 | SolarEdge | Roof Mount | Yes | No | Truss | No | No | A* | 87.2 | 41.1 | 64.2 | 2 | 0 | Asphalt Shingles | RT Mini | Portrait | 1 | Fall | 128:30 | 5 | 5 | 2 | 51:24 | 179:54 | 7 | This is the time for both this project and the one below combined
178 | 44 mins | 40° | 180° | 23 | 8.97 | Enphase | Roof Mount | Yes | No | Truss | No | No | A1 | 69.06 | 43.15 | 46.3 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Spring | 31:15 | 1 | 3 | 0 | 0:00 | 31:15 | 3
179 | 7 mins | 14° | 260° | 36 | 14.4 | Enphase | Roof Mount | Yes | Yes | Truss | No | Yes | B2 | 71.7 | 40 | 45 | 2 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Spring | 38:45 | 2 | 3 | 0 | 0:00 | 38:45 | 3
180 | 24 mins | 26° | 205° | 12 | 4.68 | SolarEdge | Roof Mount | Yes | No | Truss | No | Yes | A1 | 69.06 | 43.15 | 46.3 | 2 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Spring | 52:25 | 2 | 3 | 0 | 0:00 | 52:25 | 3
181 | 7 mins | 30° | 180° | 16 | 6.4 | Enphase | Roof Mount | Yes | Yes | Truss | No | Yes | A1 | 71.7 | 40 | 45 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Spring | 34:15 | 1 | 5 | 0 | 0:00 | 34:15 | 5
182 | 58 mins | 40° | 165° | 46 | 18.4 | Enphase | Roof Mount | Yes | Yes | Truss | No | No | A1 | 71.7 | 40 | 45 | 4 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Spring | 91:35 | 3 | 5 | 1 | 18:19 | 109:54 | 6
183 | 21 mins | 20° | 100°/190° | 26 | 10.14 | Enphase | Roof Mount | Yes | Yes | Rafter | Yes | Yes | A2 | 69.06 | 43.15 | 46.3 | 3 | 9 | Asphalt Shingles | Flashfoot 2 | Both | 2 | Spring | 76:45 | 4 | 3 | 0 | 0:00 | 76:45 | 3
184 | 13 mins | 20° | 190° | 20 | 7.8 | Enphase | Roof Mount | Yes | No | Truss | No | No | A1 | 69.06 | 43.15 | 46.3 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Spring | 24:00 | 2 | 2 | 1 | 12:00 | 36:00 | 3
185 | 9 mins | 30° | 122° | 18 | 7.29 | Enphase | Roof Mount | Yes | Yes | Truss | No | Yes | A1 | 71.7 | 40 | 45 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Summer | 32:35 | 1 | 4 | 0 | 0:00 | 32:35 | 4
186 | 20 mins | 27° | 180° | 21 | 8.505 | Enphase | Roof Mount | Yes | No | Truss | No | No | A1 | 71.7 | 40 | 45 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Spring | 32:45 | 2 | 2 | 1 | 16:22 | 49:08 | 3
187 | 28 mins | 32° | 180° | 45 | 17.55 | SolarEdge | Roof Mount | Yes | No | Truss | No | No | B1 | 69.06 | 43.15 | 46.3 | 3 | 0 | Asphalt Shingles | Unknown | Portrait | 1 | Fall | 75:30 | 4 | 4 | 1 | 18:52 | 94:22 | 5
188 | 25 mins | 26° | 90° | 24 | 9.72 | Enphase | Roof Mount | Yes | Yes | Truss | No | No | A1 | 71.7 | 40 | 45 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Spring | 35:30 | 2 | 3 | 0 | 0:00 | 35:30 | 3
189 | 21 mins | 34° | 100° | 18 | 7.29 | Enphase | Roof Mount | Yes | No | Truss | No | No | A4 | 71.7 | 40 | 45 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Spring | 18:30 | 1 | 2 | 1 | 9:15 | 27:45 | 3
190 | 17 mins | 17° | 260° | 33 | 13.365 | Enphase | Roof Mount | Yes | Yes | Rafter | No | No | A1 | 71.7 | 40 | 45 | 2 | 0 | Asphalt Shingles | Unknown | Portrait | 2 | Spring | 38:45 | 2 | 2 | 0 | 0:00 | 38:45 | 2
191 | 30 mins | 30°/35° | 255°/165° | 18 | 7.29 | Enphase | Roof Mount | Yes | No | Truss | No | No | A1 | 71.7 | 40 | 45 | 3 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Summer | 46:00 | 3 | 4 | 0 | 0:00 | 46:00 | 4
192 | 21 mins | 27° | 195° | 18 | 7.29 | Enphase | Roof Mount | Yes | No | Truss | No | No | A4 | 71.7 | 40 | 45 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Summer | 36:30 | 1 | 4 | 0 | 0:00 | 36:30 | 4
193 | 14 mins | 23° | 210° | 26 | 10.53 | Enphase | Roof Mount | Yes | No | Truss | No | No | A3 | 71.7 | 40 | 45 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Summer | 57:05 | 2 | 4 | 0 | 0:00 | 57:05 | 4
194 | 25 mins | 30° | 180° | 44 | 23.54 | Enphase | Ground Mount | Yes | Yes | Grount Mount | No | No | C3 | 89.69 | 44.65 | 70.11 | 1 | 0 | Ground Mount | Ground Mount | Landscape | 0 | Summer | 195:25 | 5 | 5 | 1 | 39:05 | 234:30 | 6
195 | 19 mins | 30° | 180° | 38 | 15.39 | Enphase | Roof Mount | Yes | No | Truss | No | No | A1 | 71.7 | 40 | 45 | 2 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Summer | 125:35 | 4 | 5 | 1 | 25:07 | 150:42 | 6
196 | 12 mins | 17° | 180° | 17 | 6.885 | Enphase | Roof Mount | Yes | Yes | Truss | No | No | A1 | 71.7 | 40 | 45 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Spring | 24:30 | 1 | 3 | 0 | 0:00 | 24:30 | 3
197 | 28 mins | 27° | 90° | 18 | 7.29 | Enphase | Roof Mount | No | No | Truss | No | Yes | A1 | 71.7 | 40 | 45 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Summer | 38:00 | 1 | 5 | 0 | 0:00 | 38:00 | 5
198 | 14 mins | 19° | 262° | 20 | 8.1 | Enphase | Roof Mount | Yes | Yes | Rafter | No | No | A1 | 71.7 | 40 | 45 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Summer | 54:15 | 2 | 4 | 0 | 0:00 | 54:15 | 4
199 | 1 hour 2 mins | 22.6° | 180° | 18 | 7.29 | Enphase | Roof Mount | No | No | Rafter | No | No | A1 | 71.7 | 40 | 45 | 1 | 0 | Standing Seam Metal Roof | S-5! | Portrait | 2 | Summer | 57:40 | 2 | 5 | 0 | 0:00 | 57:40 | 5
200 | 1 hour 3 mins | 14° | 180° | 15 | 6.15 | Enphase | Roof Mount | Yes | No | Rafter | No | No | A4 | 73.4 | 40.5 | 45.8 | 1 | 0 | Asphalt Shingles | Unknown | Landscape | 1 | Summer | 48:50 | 1 | 5 | 0 | 0:00 | 48:50 | 5
201 | 27 mins | 27° | 170° | 16 | 6.48 | Enphase | Roof Mount | Yes | Yes | Truss | No | Yes | A1 | 71.7 | 40 | 45 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Summer | 37:35 | 1 | 5 | 0 | 0:00 | 37:35 | 5
202 | 41 mins | 22.6° | 195° | 18 | 7.29 | Enphase | Roof Mount | Yes | No | Truss | No | No | A1 | 71.7 | 40 | 45 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Summer | 38:25 | 2 | 5 | 0 | 0:00 | 38:25 | 5 | New Construction - Lots of trips
203 | 36 mins | 30° | 180° | 20 | 9 | SolarEdge | Ground Mount | No | No | Grount Mount | No | No | A1 | 84.06 | 41.19 | 68.34 | 2 | 0 | Ground Mount | Ground Mount | Portrait | 0 | Summer | 104:50 | 3 | 4 | 1 | 26:12 | 131:02 | 5 | Long Trench
204 | 28 mins | 26.6° | 190° | 22 | 8.91 | Enphase | Roof Mount | Yes | Yes | Truss | No | No | B* | 71.7 | 40 | 45 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Summer | 30:30 | 1 | 4 | 0 | 0:00 | 30:30 | 4
205 | 7 mins | 22.6° | 90°/180°/270° | 28 | 11.34 | Enphase | Roof Mount | Yes | Yes | Truss | No | Yes | A1 | 71.7 | 40 | 45 | 3 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Summer | 69:20 | 2 | 5 | 0 | 0:00 | 69:20 | 5
206 | 7 mins | 18.4° | 225° | 6 | 2.34 | Enphase | Roof Mount | Yes | No | Truss | No | Yes | A4 | 69.06 | 43.15 | 46.3 | 1 | 0 | Asphalt Shingles | Unknown | Portrait | 1 | Summer | 58:30 | 3 | 5 | 0 | 0:00 | 58:30 | 5 | Detached building + trench
207 | 12 mins | 22° | 180°/270° | 30 | 12.15 | Enphase | Roof Mount | No | Yes | Truss | No | No | A* | 71.7 | 40 | 45 | 4 | 0 | Standing Seam Metal Roof | S-5! | Portrait | 2 | Summer | 67:40 | 3 | 5 | 0 | 0:00 | 67:40 | 5
208 | 23 mins | 21° | 180° | 8 | 3.24 | Enphase | Roof Mount | Yes | No | Rafter | Yes | Yes | A4 | 71.7 | 40 | 45 | 1 | 1 | Asphalt Shingles | RT Mini | Landscape | 2 | Summer | 36:00 | 1 | 4 | 0 | 0:00 | 36:00 | 4
209 | 28 mins | 38° | 180° | 13 | 5.07 | Enphase | Roof Mount | Yes | No | Truss | No | No | A1 | 69.06 | 43.15 | 46.3 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Summer | 33:10 | 1 | 4 | 0 | 0:00 | 33:10 | 4
210 | 34 mins | 18.4° | 165° | 30 | 12.15 | Enphase | Roof Mount | Yes | Yes | Truss | No | No | A1 | 71.7 | 40 | 45 | 2 | 0 | Asphalt Shingles | RT Mini | Portrait | 2 | Summer | 84:25 | 2 | 5 | 0 | 0:00 | 84:25 | 5 | New Construction
211 | 29 mins | 26.6° | 180° | 20 | 8.1 | Enphase | Roof Mount | Yes | Yes | Truss | No | No | A1 | 71.7 | 40 | 45 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Summer | 34:15 | 1 | 4 | 0 | 0:00 | 34:15 | 4
212 | 24 mins | 50° | 90°/180°/270° | 13 | 5.265 | Enphase | Roof Mount | Yes | No | Rafter | Yes | Yes | C1 | 71.7 | 40 | 45 | 4 | 3 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Fall | 71:15 | 2 | 4 | 0 | 0:00 | 71:15 | 4
213 | 23 mins | 9.5° | 0° | 32 | 12.48 | Enphase | Roof Mount | Yes | Yes | TJI | No | Yes | A* | 69.06 | 43.15 | 46.3 | 1 | 0 | Standing Seam Metal Roof | S-5! | Portrait | 3 | Summer | 67:30 | 2 | 4 | 1 | 16:52 | 84:22 | 5 | Really weird project
214 | 29 mins | 30° | 18° | 48 | 23.28 | SolarEdge | Ground Mount | No | No | Grount Mount | No | No | C3 | 87.2 | 41.1 | 64.2 | 2 | 0 | Ground Mount | Ground Mount | Portrait | 0 | Fall | 117:00 | 4 | 4 | 1 | 29:15 | 146:15 | 5 | Long trench
215 | 28 mins | 18° | 185° | 25 | 10.125 | Enphase | Roof Mount | Yes | Yes | Truss | No | No | A2 | 71.7 | 40 | 45 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Summer | 66:50 | 2 | 5 | 0 | 0:00 | 66:50 | 5
216 | 21 mins | 26° | 180° | 26 | 10.53 | Enphase | Roof Mount | Yes | No | Truss | No | No | A1 | 71.7 | 40 | 45 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Fall | 36:45 | 1 | 4 | 0 | 0:00 | 36:45 | 4
217 | 21 mins | 26° | 180° | 35 | 14.175 | Enphase | Roof Mount | Yes | Yes | Truss | No | No | C1 | 71.7 | 40 | 45 | 4 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Fall | 78:15 | 3 | 4 | 0 | 0:00 | 78:15 | 4
218 | 25 mins | 18.4° | 180° | 26 | 10.53 | Enphase | Roof Mount | Yes | Yes | Truss | No | No | A3 | 71.7 | 40 | 45 | 3 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Fall | 65:45 | 2 | 4 | 0 | 0:00 | 65:45 | 4
219 | 23 mins | 24° | 215° | 6 | 2.34 | Enphase | Roof Mount | Yes | No | Truss | No | No | A* | 69.06 | 43.15 | 46.3 | 1 | 0 | Asphalt Shingles | Flashview | Portrait | 1 | Fall | 73:30 | 3 | 4 | 0 | 0:00 | 73:30 | 4 | system addition
220 | 27 mins | 24° | 180° | 16 | 6.48 | Enphase | Roof Mount | Yes | No | Truss | No | Yes | B1 | 71.7 | 40 | 45 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Fall | 35:30 | 1 | 4 | 0 | 0:00 | 35:30 | 4
222 | 20 mins | 30° | 160° | 39 | 15.795 | Enphase | Roof Mount | Yes | Yes | Truss | No | No | A* | 71.7 | 40 | 45 | 2 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Fall | 70:00 | 3 | 4 | 0 | 0:00 | 70:00 | 4
223 | 28 mins | 10° | 90° | 18 | 7.02 | Enphase | Roof Mount | Yes | No | TJI | No | Yes | A1 | 69.06 | 43.15 | 46.3 | 1 | 0 | Asphalt Shingles | RT Mini | Landscape | 1 | Fall | 62:30 | 3 | 4 | 1 | 15:38 | 78:08 | 5 | New Construction
224 | 18 mins | 30° | 180°/90° | 20 | 8.2 | Enphase | Roof Mount | Yes | No | Truss | No | No | A4 | 73.4 | 40.5 | 45.8 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Both | 2 | Fall | 37:45 | 1 | 4 | 0 | 0:00 | 37:45 | 4
225 | 30 mins | 27°/8° | 270°/180°/90° | 28 | 11.34 | Enphase | Roof Mount | Yes | Yes | Truss | No | No | A1 | 71.7 | 40 | 45 | 3 | 0 | Asphalt Shingles | Unknown | Portrait | 2 | Fall | 58:15 | 2 | 4 | 0 | 0:00 | 58:15 | 4
226 | 39 mins | 33° | 165° | 26 | 10.53 | Enphase | Roof Mount | Yes | Yes | Truss | No | No | A1 | 71.7 | 40 | 45 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Fall | 27:45 | 1 | 4 | 0 | 0:00 | 27:45 | 4
227 | 21 mins | 30° | 135° | 22 | 8.91 | Enphase | Roof Mount | Yes | Yes | Rafter | Yes | Yes | B2 | 71.7 | 40 | 45 | 2 | 11 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Fall | 56:00 | 3 | 4 | 0 | 0:00 | 56:00 | 4
228 | 51 mins | 30° | 180° | 20 | 9.6 | SolarEdge | Ground Mount | No | No | Grount Mount | No | No | C* | 87.2 | 41.1 | 64.2 | 1 | 0 | Ground Mount | Ground Mount | Landscape | 0 | Fall | 90:45 | 3 | 4 | 1 | 22:41 | 113:26 | 5
229 | 26 mins | 17° | 165°/225° | 26 | 10.53 | Enphase | Roof Mount | Yes | Yes | Rafter | Yes | No | A1 | 71.7 | 40 | 45 | 3 | 18 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Fall | 58:00 | 3 | 4 | 0 | 0:00 | 58:00 | 4 | Some rework after the fact, but I don't think it's included in the time tracking data
230 | 29 mins | 27° | 180° | 20 | 7.8 | Enphase | Roof Mount | Yes | No | Rafter | Yes | No | A1 | 69.06 | 43.15 | 46.3 | 1 | 10 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Winter | 57:15 | 2 | 4 | 0 | 0:00 | 57:15 | 4
231 | 20 mins | 27° | 170° | 24 | 9.36 | SolarEdge | Roof Mount | Yes | No | TJI | No | No | A1 | 69.06 | 43.15 | 46.3 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Winter | 50:45 | 2 | 4 | 0 | 0:00 | 50:45 | 4
232 | 42 mins | 26° | 180° | 2 | 0.74 | N/A | Roof Mount |  |  | Rafter | Yes | No | A1 | 70.67 | 39.98 | 41.9 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Fall | 6:00 | 1 | 1 | 1 | 6:00 | 12:00 | 2
233 | 31 mins | 18° | 90° | 20 | 8.1 | Enphase | Roof Mount | Yes | No | Rafter | Yes | No | A1 | 71.7 | 40 | 45 | 1 | 12 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Fall | 35:15 | 1 | 4 | 0 | 0:00 | 35:15 | 4
238 | 20 mins | 18.4° | 180° | 8 | 3.24 | Enphase | Roof Mount | No | No | Purlin | No | Yes | A1 | 71.7 | 40 | 45 | 1 | 0 | Ag Metal | Ejot | Landscape | 1 | Fall | 45:00 | 2 | 4 | 0 | 0:00 | 45:00 | 4
239 | 26 mins | 18.4° | 180°/270° | 26 | 10.53 | Enphase | Roof Mount | Yes | Yes | Truss | No | Yes | A1 | 71.7 | 40 | 45 | 2 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Winter | 58:45 | 2 | 4 | 0 | 0:00 | 58:45 | 4
240 | 30 mins | 17.5° | 180° | 60 | 24.3 | Enphase | Roof Mount | No | No | Purlin | No | No | C3 | 71.7 | 40 | 45 | 1 | 0 | Ag Metal | Ejot | Landscape | 1 | Summer | 89:45 | 3 | 4 | 0 | 0:00 | 89:45 | 4
241 | 40 mins | 22.6° | 225° | 16 | 6.48 | Enphase | Roof Mount | No | No | Truss | No | No | A1 | 71.7 | 40 | 45 | 1 | 0 | Standing Seam Metal Roof | S-5! | Portrait | 1 | Spring | 31:15 | 1 | 4 | 0 | 0:00 | 31:15 | 4
242 | 52 mins | 17° | 176°/86° | 40 | 17.6 | SolarEdge | Roof Mount | Yes | No | Truss | No | No | C2 | 89.69 | 44.65 | 57.32 | 2 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Winter | 71:05 | 4 | 4 | 0 | 0:00 | 71:05 | 4
244 | 7 mins | 33.7° | 180° | 7 | 2.835 | Enphase | Roof Mount | Yes | No | Rafter | No | Yes | A1 | 71.7 | 40 | 45 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Winter | 29:00 | 1 | 4 | 0 | 0:00 | 29:00 | 4
245 | 27 mins | 19° | 180° | 18 | 7.29 | Enphase | Roof Mount | Yes | No | Truss | No | Yes | A1 | 71.7 | 40 | 45 | 3 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Winter | 59:30 | 2 | 4 | 0 | 0:00 | 59:30 | 4
246 | 30 mins | 18° | 206°/116° | 19 | 7.695 | Enphase | Roof Mount | Yes | No | Rafter | No | No | A4 | 71.7 | 40 | 45 | 2 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Winter | 34:30 | 1 | 4 | 0 | 0:00 | 34:30 | 4
247 | 25 mins | 18°/27° | 225°/135°/45° | 16 | 7.04 | GoodWe | Roof Mount | Yes | No | Truss | No | No | A1 | 89.69 | 44.65 | 57.32 | 3 | 0 | Asphalt Shingles | Flashview | Both | 2 | Spring | 40:40 | 2 | 4 | 0 | 0:00 | 40:40 | 4 | Adjusted direct time due to time tracking errors
248 | 25 mins | 18°/27° | 225°/135° | 16 | 7.04 | GoodWe | Roof Mount | Yes | No | Truss | No | No | A1 | 89.69 | 44.65 | 57.32 | 2 | 0 | Asphalt Shingles | Flashview | Both | 2 | Spring | 40:40 | 3 | 4 | 0 | 0:00 | 40:40 | 4 | Adjusted direct time due to time tracking errors
249 | 25 mins | 18°/27° | 225°/135°/45° | 16 | 7.04 | GoodWe | Roof Mount | Yes | No | Truss | No | No | A1 | 89.69 | 44.65 | 57.32 | 3 | 0 | Asphalt Shingles | Flashview | Both | 2 | Spring | 40:40 | 2 | 4 | 0 | 0:00 | 40:40 | 4 | Adjusted direct time due to time tracking errors
250 | 25 mins | 18°/27° | 225°/135° | 16 | 7.04 | GoodWe | Roof Mount | Yes | No | Truss | No | No | A1 | 89.69 | 44.65 | 57.32 | 2 | 0 | Asphalt Shingles | Flashview | Both | 2 | Spring | 40:40 | 2 | 4 | 0 | 0:00 | 40:40 | 4 | Adjusted direct time due to time tracking errors
251 | 50 mins | 22.6° | 230° | 36 | 15.12 | SolarEdge | Roof Mount | Yes | No | Truss | No | No | C3 | 68.1 | 44 | 47.4 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 3 | Winter | 86:45 | 5 | 4 | 0 | 0:00 | 86:45 | 4
252 | 23 mins | 38° | 135°/225° | 13 | 5.265 | Enphase | Roof Mount | Yes | Yes | Rafter | Yes | Yes | A1 | 71.7 | 40 | 45 | 3 | 10 | Asphalt Shingles | Hugs | Portrait | 1 | Spring | 61:15 | 2 | 4 | 0 | 0:00 | 61:15 | 4
253 | 9 mins | 33° | 185°/95° | 26 | 10.53 | Enphase | Roof Mount | Yes | Yes | Truss | No | Yes | A4 | 71.7 | 40 | 45 | 3 | 0 | Asphalt Shingles | RT Mini | Both | 1 | Winter | 58:15 | 3 | 4 | 0 | 0:00 | 58:15 | 4
254 | 36 mins | 27° | 200°/110° | 33 | 13.365 | Enphase | Roof Mount | Yes | Yes | Truss | No | No | A1 | 71.7 | 40 | 45 | 3 | 0 | Asphalt Shingles | Flashfoot 2 | Both | 2 | Spring | 79:15 | 2 | 5 | 0 | 0:00 | 79:15 | 5
255 | 27 mins | 18.4 | 180° | 20 | 8.1 | Enphase | Roof Mount | Yes | Yes | Truss | No | Yes | A1 | 71.7 | 40 | 45 | 1 | 0 | Asphalt Shingles | Hugs | Portrait | 1 | Winter | 33:30 | 1 | 4 | 0 | 0:00 | 33:30 | 4
256 | 21 mins | 35° | 180° | 26 | 10.53 | Enphase | Roof Mount | Yes | Yes | Truss | No | No | C1 | 71.7 | 40 | 45 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Spring | 70:30 | 3 | 3 | 0 | 0:00 | 70:30 | 3 | High winds slowed us down
257 | 25 mins | 24°/14° | 90°/180°/270° | 25 | 10 | Enphase | Roof Mount | Yes | No | Truss | No | Yes | A4 | 74.8 | 40.9 | 48 | 4 | 0 | Asphalt Shingles | Unknown | Both | 2 | Spring | 62:15 | 2 | 4 | 0 | 0:00 | 62:15 | 4
258 | 46 mins | 18° | 220°/130° | 20 | 8 | Enphase | Roof Mount | Yes | Yes | Truss | No | No | A1 | 74.8 | 40.9 | 48 | 2 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Winter | 78:15 | 3 | 4 | 1 | 19:34 | 97:49 | 5
259 | 18 mins | 45° | 90° | 18 | 7.2 | Enphase | Roof Mount | Yes | No | Rafter | No | Yes | A1 | 74.8 | 40.9 | 48 | 1 | 0 | Asphalt Shingles | Flashview | Portrait | 1 | Spring | 39:00 | 2 | 3 | 0 | 0:00 | 39:00 | 3
260 | 46 mins | 10° | 185° | 47 | 18.8 | Enphase | Roof Mount | No | No | Truss | No | No | C3 | 74.8 | 40.9 | 48 | 1 | 0 | Standing Seam Metal Roof | S-5! | Portrait | 1 | Spring | 53:30 | 2 | 3 | 0 | 0:00 | 53:30 | 3
261 | 27 mins | 27° | 180°/90° | 13 | 5.2 | Enphase | Roof Mount | Yes | Yes | Truss | No | Yes | A4 | 74.8 | 40.9 | 48 | 2 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Spring | 24:00 | 1 | 3 | 0 | 0:00 | 24:00 | 3
262 | 26 mins | 26° | 90°/180° | 12 | 4.86 | Enphase | Roof Mount | Yes | No | Truss | No | Yes | A1 | 71.7 | 40 | 45 | 2 | 0 | Asphalt Shingles | Flashview | Portrait | 1 | Spring | 38:00 | 2 | 4 | 0 | 0:00 | 38:00 | 4
263 | 26 mins | 26° | 225° | 12 | 4.86 | Enphase | Roof Mount | Yes | No | Truss | No | Yes | A1 | 71.7 | 40 | 45 | 2 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Spring | 25:15 | 1 | 4 | 0 | 0:00 | 25:15 | 4
264 | 26 mins | 26° | 90°/180° | 12 | 4.86 | Enphase | Roof Mount | Yes | No | Truss | No | Yes | A1 | 71.7 | 40 | 45 | 3 | 0 | Asphalt Shingles | Flashview | Portrait | 1 | Winter | 41:00 | 2 | 3 | 0 | 0:00 | 41:00 | 3
265 | 30 mins | 34° | 110°/200° | 31 | 12.555 | Enphase | Roof Mount | Yes | Yes | Truss | No | Yes | A1 | 71.7 | 40 | 45 | 3 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Spring | 101:15 | 6 | 4 | 0 | 0:00 | 101:15 | 4 | Rough electrical ahead of time. Also installed an EV charger
266 | 24 mins | 27° | 220° | 14 | 5.6 | Enphase | Roof Mount | Yes | Yes | Truss | No | No | C2 | 74.8 | 40.9 | 48 | 1 | 0 | Asphalt Shingles | Flashview | Portrait | 1 | Spring | 37:15 | 2 | 4 | 0 | 0:00 | 37:15 | 4
267 | 31 mins | 20 | 100/190 | 34 | 13.77 | Enphase | Roof Mount | Yes | Yes | Truss | No | No | A1 | 71.7 | 40 | 45 | 4 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Spring | 86:30 | 4 | 5 | 0 | 0:00 | 86:30 | 5
268 | 28 mins | 18° | 170° | 24 | 9.6 | Enphase | Roof Mount | Yes | No | Truss | No | No | A1 | 74.8 | 40.9 | 48 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Spring | 26:30 | 1 | 3 | 0 | 0:00 | 26:30 | 3
269 | 20 mins | 33° | 145°/232° | 20 | 8 | Enphase | Roof Mount | Yes | Yes | Truss | No | No | A3 | 74.8 | 40.9 | 48 | 3 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Spring | 67:30 | 2 | 5 | 0 | 0:00 | 67:30 | 5
270 | 30 mins | 18° | 180° | 19 | 7.6 | Enphase | Roof Mount | No | No | Truss | No | No | A1 | 74.8 | 40.9 | 48 | 1 | 0 | Standing Seam Metal Roof | S-5! | Portrait | 1 | Spring | 52:45 | 2 | 4 | 0 | 0:00 | 52:45 | 4
271 | 48 mins | 30° | 180° | 22 | 10.67 | SolarEdge | Ground Mount | No | No | Grount Mount | No | No | A4 | 87.2 | 41.1 | 64.2 | 1 | 0 | Ground Mount | Ground Mount | Portrait | 0 | Spring | 75:45 | 2 | 4 | 0 | 0:00 | 75:45 | 4
272 | 29 mins | 27° | 180° | 26 | 10.4 | Enphase | Roof Mount | Yes | No | Truss | No | No | A3 | 74.8 | 40.9 | 48 | 2 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Spring | 38:00 | 1 | 4 | 0 | 0:00 | 38:00 | 4
273 | 56 mins | 30 | 180 | 22 | 10.67 | SolarEdge | Ground Mount | No | No | Grount Mount | No | No | A* | 87.2 | 41.1 | 64.2 | 1 | 0 | Ground Mount | Ground Mount | Portrait | 0 | Spring | 55:30 | 3 | 4 | 0 | 0:00 | 55:30 | 4 | Trenching
274 | 23 mins | 34° | 210° | 40 | 16 | Enphase | Roof Mount | Yes | Yes | Truss | No | No | A1 | 74.8 | 40.9 | 48 | 1 | 0 | Asphalt Shingles | Flashview | Portrait | 1 | Spring | 53:30 | 2 | 3 | 0 | 0:00 | 53:30 | 3 | Some electrical re-work after the fact, but I don't think it's included in the time tracking
275 | 47 mins | 22.6° | 90° | 40 | 16 | Enphase | Roof Mount | No | No | Purlin | Yes | No | B2 | 74.8 | 40.9 | 48 | 1 | 56 | Ag Metal | Ejot | Landscape | 1 | Fall | 83:45 | 3 | 5 | 0 | 0:00 | 83:45 | 5 | A super weird one
276 | 11 mins | 45 | 195 | 12 | 4.8 | Enphase | Roof Mount | No | No | Rafter | No | Yes | A1 | 74.8 | 40.9 | 48 | 1 | 0 | Standing Seam Metal Roof | S-5! | Portrait | 1 | Spring | 40:15 | 2 | 4 | 0 | 0:00 | 40:15 | 4
277 | 11 mins | 47° | 195 | 21 | 8.505 | Enphase | Roof Mount | Yes | Yes | Rafter | No | Yes | A1 | 71.7 | 40 | 45 | 2 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Spring | 49:00 | 3 | 4 | 0 | 0:00 | 49:00 | 4
278 | 26 mins | 18.4° | 236° | 28 | 11.2 | Enphase | Roof Mount | Yes | No | Truss | No | No | A1 | 74.8 | 40.9 | 48 | 2 | 0 | Asphalt Shingles | Flashview | Portrait | 2 | Spring | 16:30 | 1 | 2 | 0 | 0:00 | 16:30 | 2
279 | 28 mins | 27 | 180 | 30 | 12 | Enphase | Roof Mount | Yes | No | Truss | No | No | A4 | 74.8 | 40.9 | 48 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Summer | 75:15 | 2 | 5 | 0 | 0:00 | 75:15 | 5
280 | 26 mins | 27 | 210 | 12 | 4.8 | Enphase | Roof Mount | Yes | No | Truss | No | Yes | A1 | 71.7 | 40 | 45 | 2 | 0 | Asphalt Shingles | Flashview | Portrait | 1 | Summer | 30:00 | 1 | 5 | 0 | 0:00 | 30:00 | 5
281 | 26 mins | 27 | 120/210 | 12 | 4.8 | Enphase | Roof Mount | Yes | No | Truss | No | Yes | A1 | 71.7 | 40 | 45 | 2 | 0 | Asphalt Shingles | Flashview | Portrait | 1 | Summer | 30:00 | 1 | 5 | 0 | 0:00 | 30:00 | 5
282 | 26 mins | 27 | 129 | 12 | 4.8 | Enphase | Roof Mount | Yes | No | Truss | No | Yes | A1 | 71.7 | 40 | 45 | 2 | 0 | Asphalt Shingles | Flashview | Portrait | 1 | Summer | 25:00 | 1 | 5 | 0 | 0:00 | 25:00 | 5
283 | 26 mins | 27 | 135 | 12 | 4.8 | Enphase | Roof Mount | Yes | No | Truss | No | Yes | A1 | 71.7 | 40 | 45 | 1 | 0 | Asphalt Shingles | Flashview | Portrait | 1 | Summer | 30:30 | 2 | 5 | 0 | 0:00 | 30:30 | 5
284 | 27 mins | 27 | 146 | 12 | 4.8 | Enphase | Roof Mount | Yes | No | Truss | No | Yes | A2 | 71.7 | 40 | 45 | 2 | 0 | Asphalt Shingles | Flashview | Portrait | 1 | Summer | 34:00 | 1 | 5 | 0 | 0:00 | 34:00 | 5
285 | 24 mins | 16.5 | 150 | 12 | 5.04 | Enphase | Roof Mount | Yes | Yes | Rafter | Yes | Yes | A1 | 73.4 | 40.9 | 47.8 | 1 | 10 | Asphalt Shingles | Unknown | Portrait | 1 | Summer | 38:30 | 1 | 5 | 0 | 0:00 | 38:30 | 5
286 | 29 mins | 25 | 180 | 12 | 4.8 | Enphase | Roof Mount | Yes | No | Truss | No | Yes | A1 | 74.8 | 40.9 | 48 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Summer | 48:15 | 2 | 5 | 0 | 0:00 | 48:15 | 5
287 | 23 mins | 27 | 267 | 24 | 9.6 | Enphase | Roof Mount | Yes | No | Truss | No | No | A1 | 74.8 | 40.9 | 48 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Summer | 36:30 | 1 | 5 | 0 | 0:00 | 36:30 | 5
288 | 8 mins | 33.7 | 260 | 16 | 6.72 | Enphase | Roof Mount | Yes | No | Rafter | No | Yes | A1 | 73.4 | 40.9 | 47.8 | 3 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Summer | 44:45 | 2 | 5 | 0 | 0:00 | 44:45 | 5
289 | 9 mins | 27 | 182 | 17 | 7.82 | Enphase | Roof Mount | Yes | Yes | Truss | No | Yes | A1 | 68 | 47.4 | 50 | 3 | 0 | Asphalt Shingles | Flashfoot 2 | Both | 2 | Summer | 47:30 | 1 | 5 | 0 | 0:00 | 47:30 | 5
290 | 46 mins | 33/37 | 247/157/67 | 26 | 10.92 | Enphase | Roof Mount | Yes | No | Rafter | Yes | No | A1 | 73.4 | 40.9 | 47.8 | 3 | 17 | Asphalt Shingles | Hugs | Portrait | 2 | Summer | 90:30 | 2 | 5 | 0 | 0:00 | 90:30 | 5
291 | 13 mins | 18.4/9.4 | 178.5 | 36 | 14.4 | Enphase | Roof Mount | Yes | No | Truss | No | No | A1 | 74.8 | 40.9 | 48 | 2 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Summer | 73:45 | 2 | 5 | 0 | 0:00 | 73:45 | 5 | New Construction
292 | 8 mins | 45 | 180 | 14 | 5.6 | Enphase | Roof Mount | Yes | Yes | Truss | No | Yes | A1 | 74.8 | 40.9 | 48 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Summer | 35:00 | 1 | 4 | 0 | 0:00 | 35:00 | 4
293 | 4 mins | 27 | 226 | 12 | 4.8 | Enphase | Roof Mount | Yes | No | Truss | No | Yes | A1 | 74.8 | 40.9 | 48 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Summer | 40:00 | 1 | 5 | 0 | 0:00 | 40:00 | 5
294 | 38 mins | 26 | 168 | 13 | 5.2 | Enphase | Roof Mount | Yes | No | Truss | No | No | A4 | 74.8 | 40.9 | 48 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Summer | 36:30 | 1 | 5 | 0 | 0:00 | 36:30 | 5
295 | 27 mins | 33.7 | 175 | 16 | 7.36 | Enphase | Roof Mount | Yes | Yes | Truss | No | Yes | A1 | 68 | 47.4 | 50 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Both | 2 | Summer | 44:30 | 1 | 5 | 0 | 0:00 | 44:30 | 5
296 | 28 mins | 18 | 260 | 18 | 7.2 | Enphase | Roof Mount | Yes | Yes | Rafter | No | Yes | A1 | 74.8 | 40.9 | 48 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Summer | 33:15 | 1 | 4 | 0 | 0:00 | 33:15 | 4
297 | 41 mins | 18.4 | 84 | 33 | 13.53 | Enphase | Roof Mount | No | No | Purlin | No | No | C* | 69.37 | 44.65 | 47 | 1 | 0 | Ag Metal | Ejot | Landscape | 1 | Summer | 78:15 | 2 | 5 | 0 | 0:00 | 78:15 | 5
298 | 23 mins | 18.4 | 189.4 | 9 | 3.6 | Enphase | Roof Mount | Yes | No | Truss | No | Yes | A1 | 74.8 | 40.9 | 48 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Landscape | 2 | Summer | 40:15 | 1 | 5 | 0 | 0:00 | 40:15 | 5
299 | 29 mins | 30 | 148 | 26 | 10.92 | Enphase | Roof Mount | Yes | Yes | Truss | No | No | A1 | 73.4 | 40.9 | 47.8 | 2 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Summer | 54:15 | 1 | 5 | 0 | 0:00 | 54:15 | 5
300 | 20 mins | 33/40 | 134/223 | 32 | 12.8 | Enphase | Roof Mount | Yes | Yes | Truss | No | No | C3 | 74.8 | 40.9 | 48 | 2 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Summer | 69:30 | 2 | 5 | 0 | 0:00 | 69:30 | 5
301 | 19 mins | 34 | 180 | 18 | 8.28 | Enphase | Roof Mount | Yes | No | Truss | No | No | A1 | 68 | 47.4 | 50 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Summer | 46:00 | 1 | 5 | 0 | 0:00 | 46:00 | 5
302 | 25 mins | 33 | 90/180/270 | 18 | 7.2 | Enphase | Roof Mount | Yes | Yes | Truss | No | Yes | A1 | 74.8 | 40.9 | 48 | 3 | 0 | Asphalt Shingles | Flashfoot 2 | Both | 2 | Summer | 67:00 | 3 | 5 | 0 | 0:00 | 67:00 | 5
303 | 22 mins | 37.5 | 138 | 8 | 3.2 | Enphase | Roof Mount | Yes | Yes | Rafter | Yes | Yes | A1 | 74.8 | 40.9 | 48 | 1 | 12 | Asphalt Shingles | Hugs | Landscape | 1 | Summer | 40:15 | 1 | 5 | 0 | 0:00 | 40:15 | 5
304 | 25 mins | 27 | 90/180 | 21 | 9.66 | Enphase | Roof Mount | Yes | No | Truss | No | Yes | A1 | 68 | 47.4 | 50 | 2 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Summer | 49:30 | 2 | 5 | 0 | 0:00 | 49:30 | 5
305 | 28 mins | 35 | 90 | 20 | 8 | Enphase | Roof Mount | No | No | Truss | No | Yes | A1 | 74.8 | 40.9 | 48 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Both | 2 | Fall | 29:15 | 1 | 3 | 0 | 0:00 | 29:15 | 3
306 | 13 mins | 37/23 | 90/180 | 33 | 13.53 | Enphase | Roof Mount | Yes | No | Truss | No | Yes | A3 | 69.37 | 44.65 | 47 | 2 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Fall | 89:30 | 2 | 5 | 0 | 0:00 | 89:30 | 5
307 | 30 mins | 18 | 302/213 | 26 | 10.4 | Enphase | Roof Mount | Yes | Yes | Truss | No | No | A1 | 74.8 | 40.9 | 48 | 3 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Summer | 38:30 | 1 | 4 | 0 | 0:00 | 38:30 | 4
308 | 12 mins | 37 | 180 | 14 | 5.6 | Enphase | Roof Mount | Yes | No | Truss | No | Yes | A1 | 74.8 | 40.9 | 48 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Both | 2 | Fall | 43:30 | 1 | 5 | 0 | 0:00 | 43:30 | 5
309 | 18 mins | 11 | 181 | 18 | 7.2 | Enphase | Roof Mount | Yes | No | Truss | No | Yes | A1 | 74.8 | 40.9 | 48 | 2 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Summer | 42:15 | 1 | 5 | 0 | 0:00 | 42:15 | 5
310 | 8 mins | 22/36 | 138/228 | 10 | 4 | Enphase | Roof Mount | Yes | Yes | Truss | No | Yes | A1 | 74.8 | 40.9 | 48 | 3 | 0 | Asphalt Shingles | Hugs | Portrait | 1 | Summer | 30:00 | 1 | 4 | 0 | 0:00 | 30:00 | 4
311 | 31 mins | 18.4 | 189/99 | 26 | 10.14 | Enphase | Roof Mount | Yes | Yes | Truss | No | No | A1 | 69.06 | 43.15 | 46.3 | 2 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Fall | 27:30 | 1 | 3 | 0 | 0:00 | 27:30 | 3
312 | 9 mins | 19.3 | 180/90 | 17 | 6.8 | Enphase | Roof Mount | No | Yes | Rafter | Yes | Yes | C2 | 74.8 | 40.9 | 48 | 2 | 16 | Standing Seam Metal Roof | S-5! | Portrait | 1 | Fall | 46:30 | 1 | 5 | 0 | 0:00 | 46:30 | 5
313 | 47 mins | 22 | 260 | 16 | 6.4 | Enphase | Roof Mount | Yes | Yes | TJI | No | No | A3 | 74.8 | 40.9 | 48 | 1 | 0 | Asphalt Shingles | Hugs | Portrait | 1 | Fall | 39:30 | 1 | 5 | 0 | 0:00 | 39:30 | 5
314 | 19 mins | 26 | 208/116 | 22 | 8.8 | Enphase | Roof Mount | Yes | Yes | Truss | No | No | A3 | 74.8 | 40.9 | 48 | 2 | 0 | Asphalt Shingles | Hugs | Portrait | 1 | Fall | 44:45 | 2 | 5 | 0 | 0:00 | 44:45 | 5
315 | 21 mins | 33.7 | 160 | 26 | 10.66 | Enphase | Roof Mount | Yes | Yes | Truss | No | No | B* | 69.37 | 44.65 | 47 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Fall | 59:30 | 2 | 4 | 0 | 0:00 | 59:30 | 4
316 | 8 mins | 18 | 180 | 14 | 5.6 | Enphase | Roof Mount | Yes | Yes | Rafter | Yes | Yes | A* | 74.8 | 40.9 | 48 | 1 | 8 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Fall | 56:15 | 2 | 6 | 0 | 0:00 | 56:15 | 6
317 | 26 mins | 27 | 221 | 12 | 4.8 | Enphase | Roof Mount | Yes | No | Truss | No | Yes | A1 | 74.8 | 40.9 | 48 | 2 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Summer | 26:00 | 1 | 5 | 0 | 0:00 | 26:00 | 5
318 | 26 mins | 27 | 271 | 12 | 4.8 | Enphase | Roof Mount | Yes | No | Truss | No | Yes | A1 | 74.8 | 40.9 | 48 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Summer | 26:15 | 1 | 3 | 0 | 0:00 | 26:15 | 3 | Adjusted direct time due to time tracking errors
319 | 26 mins | 27 | 125 | 12 | 4.8 | Enphase | Roof Mount | Yes | No | Truss | No | Yes | A3 | 74.8 | 40.9 | 48 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Summer | 26:15 | 1 | 5 | 0 | 0:00 | 26:15 | 5 | Adjusted direct time due to time tracking errors
320 | 27 mins | 27 | 146 | 12 | 4.8 | Enphase | Roof Mount | Yes | No | Truss | No | Yes | A1 | 74.8 | 40.9 | 48 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Summer | 26:15 | 1 | 2 | 0 | 0:00 | 26:15 | 2 | Adjusted direct time due to time tracking errors
321 | 25 mins | 26 | 180 | 20 | 8.4 | Enphase | Roof Mount | Yes | Yes | Truss | No | No | A1 | 73.4 | 40.9 | 47.8 | 4 | 0 | Asphalt Shingles | Flashfoot 2 | Both | 2 | Fall | 38:30 | 2 | 5 | 0 | 0:00 | 38:30 | 5 | Adjusted direct time due to time tracking errors
322 | 24 mins | 18/27 | 179/269 | 28 | 12.88 | Enphase | Roof Mount | Yes | Yes | Rafter | No | Yes | A1 | 68 | 47.4 | 50 | 3 | 0 | Asphalt Shingles | Flashfoot 2 | Landscape | 1 | Winter | 55:00 | 2 | 5 | 0 | 0:00 | 55:00 | 5
323 | 22 mins | 18 | 90/180 | 26 | 10.66 | Enphase | Roof Mount | Yes | Yes | Rafter | Yes | Yes | A1 | 69.37 | 44.65 | 47 | 2 | 2 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Summer | 52:00 | 1 | 5 | 0 | 0:00 | 52:00 | 5
324 | 27 mins | 27 | 220/140&220 | 42 | 16.17 | Enphase | Roof Mount | Yes | No | Truss | No | No | B2 | 79.06 | 39.45 | 49.6 | 4 | 0 | Asphalt Shingles | Flashview | Portrait | 1 | Fall | 83:30 | 2 | 5 | 0 | 0:00 | 83:30 | 5
325 | 24 mins | 14 | 280/100 | 31 | 11.935 | Enphase | Roof Mount | Yes | No | Truss | No | No | B1 | 79.06 | 39.45 | 49.6 | 3 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Fall | 76:45 | 3 | 5 | 0 | 0:00 | 76:45 | 5
326 | 15 mins | 33 | 290/200 | 36 | 16.56 | Enphase | Roof Mount | Yes | Yes | Truss | No | No | C1 | 68 | 47.4 | 50 | 7 | 0 | Asphalt Shingles | Flashfoot 2 | Both | 2 | Fall | 94:00 | 3 | 4 | 1 | 23:30 | 117:30 | 5
327 | 41 mins | 26 | 90 | 22 | 8.8 | Enphase | Roof Mount | Yes | Yes | Truss | No | No | A1 | 74.8 | 40.9 | 48 | 3 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Fall | 42:30 | 1 | 5 | 0 | 0:00 | 42:30 | 5
328 | 7 mins | 22 | 91/181 | 9 | 4.14 | Enphase | Roof Mount | Yes | No | Rafter | Yes | Yes | A1 | 68 | 47.4 | 50 | 1 | 9 | Asphalt Shingles | Flashfoot 2 | Both | 1 | Fall | 39:15 | 1 | 5 | 0 | 0:00 | 39:15 | 5
329 | 20 mins | 40 | 179 | 8 | 3.36 | Enphase | Roof Mount | Yes | Yes | Rafter | Yes | Yes | A4 | 73.4 | 40.9 | 47.8 | 1 | 21 | Asphalt Shingles | Hugs | Portrait | 1 | Fall | 48:00 | 1 | 5 | 0 | 0:00 | 48:00 | 5
330 | 25 mins | 25 | 89/269 | 21 | 8.4 | Enphase | Roof Mount | Yes | Yes | Truss | No | Yes | A1 | 74.8 | 40.9 | 48 | 2 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Fall | 40:45 | 1 | 5 | 0 | 0:00 | 40:45 | 5
331 | 24 mins | 19/17 | 180 | 36 | 16.56 | Enphase | Roof Mount | Yes | Yes | Truss | No | Yes | C1 | 68 | 47.4 | 50 | 3 | 0 | Asphalt Shingles | Flashfoot 2 | Landscape | 2 | Fall | 94:15 | 4 | 5 | 0 | 0:00 | 94:15 | 5
332 | 20 mins | 18.4 | 180 | 10 | 4.25 | Enphase | Roof Mount | Yes | No | Rafter | Yes | Yes | A4 | 67.8 | 44.6 | 46.7 | 1 | 4 | Asphalt Shingles | Hugs | Portrait | 1 | Fall | 32:45 | 1 | 4 | 0 | 0:00 | 32:45 | 4
333 | 14 mins | 27 | 94/184 | 23 | 9.2 | Enphase | Roof Mount | Yes | Yes | Truss | No | No | A1 | 74.8 | 40.9 | 48 | 2 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Fall | 40:45 | 1 | 5 | 0 | 0:00 | 40:45 | 5
334 | 23 mins | 20 | 180 | 16 | 7.36 | Enphase | Roof Mount | Yes | Yes | Rafter | No | Yes | A1 | 68 | 47.4 | 50 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Landscape | 1 | Fall | 43:15 | 2 | 5 | 0 | 0:00 | 43:15 | 5
335 | 22 mins | 34 | 227 | 18 | 7.2 | Enphase | Roof Mount | Yes | Yes | Rafter | Yes | Yes | C1 | 74.8 | 40.9 | 48 | 1 | 15 | Asphalt Shingles | Hugs | Portrait | 2 | Fall | 38:30 | 1 | 4 | 0 | 0:00 | 38:30 | 4
336 | 31 mins | 27 | 102/282 | 23 | 9.2 | Enphase | Roof Mount | Yes | Yes | Truss | No | No | A1 | 74.8 | 40.9 | 48 | 2 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Fall | 37:15 | 2 | 4 | 0 | 0:00 | 37:15 | 4
337 | 22 mins | 18 | 258/78 | 18 | 7.2 | Enphase | Roof Mount | Yes | Yes | Rafter | Yes | Yes | A1 | 74.8 | 40.9 | 48 | 2 | 6 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Fall | 38:00 | 1 | 5 | 0 | 0:00 | 38:00 | 5
338 | 40 mins | 39 | 179 | 14 | 5.74 | Enphase | Roof Mount | Yes | No | Rafter | No | No | A1 | 69.37 | 44.65 | 47 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Both | 1 | Fall | 40:45 | 1 | 5 | 0 | 0:00 | 40:45 | 5
339 | 47 mins | 18.4 | 182 | 21 | 8.4 | Enphase | Roof Mount | No | No | Purlin | No | No | A2 | 74.8 | 40.9 | 48 | 1 | 0 | Ag Metal | Ejot | Landscape | 1 | Fall | 45:00 | 2 | 5 | 0 | 0:00 | 45:00 | 5
340 | 19 mins | 18.4 | 181 | 26 | 10.4 | Enphase | Roof Mount | Yes | Yes | Truss | No | No | A1 | 74.8 | 40.9 | 48 | 2 | 0 | Asphalt Shingles | Flashfoot 2 | Both | 2 | Fall | 27:15 | 1 | 4 | 0 | 0:00 | 27:15 | 4
341 | 31 mins | 33 | 165 | 25 | 10 | Enphase | Roof Mount | Yes | Yes | Truss | No | No | A1 | 74.8 | 40.9 | 48 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Both | 1 | Fall | 45:45 | 1 | 5 | 0 | 0:00 | 45:45 | 5
342 | 28 mins | 18.4 | 180 | 18 | 7.2 | Enphase | Roof Mount | Yes | Yes | Truss | No | No | A* | 74.8 | 40.9 | 48 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 0 | Winter | 36:00 | 1 | 5 | 0 | 0:00 | 36:00 | 5
343 | 25 mins | 26 | 179 | 8 | 3.2 | Enphase | Roof Mount | No | Yes | Truss | No | Yes | A1 | 74.8 | 40.9 | 48 | 1 | 0 | Standing Seam Metal Roof | S-5! | Portrait | 2 | Winter | 38:30 | 1 | 5 | 0 | 0:00 | 38:30 | 5
344 | 26 mins | 25 | 144/234 | 12 | 4.8 | Enphase | Roof Mount | Yes | No | Truss | No | Yes | A1 | 74.8 | 40.9 | 48 | 2 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Fall | 27:50 | 1 | 5 | 0 | 0:00 | 27:50 | 5 | Adjusted direct time due to time tracking errors
345 | 26 mins | 25 | 229/139 | 12 | 4.8 | Enphase | Roof Mount | Yes | No | Truss | No | Yes | A1 | 74.8 | 40.9 | 48 | 2 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Fall | 27:50 | 1 | 5 | 0 | 0:00 | 27:50 | 5 | Adjusted direct time due to time tracking errors
346 | 26 mins | 25 | 149/239 | 12 | 4.8 | Enphase | Roof Mount | Yes | No | Truss | No | Yes | A1 | 74.8 | 40.9 | 48 | 2 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Fall | 27:50 | 1 | 5 | 0 | 0:00 | 27:50 | 5 | Adjusted direct time due to time tracking errors
347 | 26 mins | 25 | 133 | 12 | 4.8 | Enphase | Roof Mount | Yes | No | Truss | No | Yes | A1 | 74.8 | 40.9 | 48 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Fall | 27:50 | 1 | 4 | 0 | 0:00 | 27:50 | 4 | Adjusted direct time due to time tracking errors
348 | 36 mins | 38 | 179 | 21 | 8.82 | Enphase | Roof Mount | Yes | Yes | Rafter | Yes | No | A1 | 73.4 | 40.9 | 47.8 | 1 | 14 | Asphalt Shingles | Hugs | Both | 2 | Fall | 85:00 | 2 | 5 | 0 | 0:00 | 85:00 | 5
350 | 23 mins | 22 | 90/180/270 | 50 | 23 | Enphase | Roof Mount | No | Yes | Rafter | Yes | Yes | C1 | 68 | 47.4 | 50 | 6 | 26 | Standing Seam Metal Roof | S-5! | Both | 1 | Winter | 185:30 | 6 | 5 | 0 | 0:00 | 185:30 | 5 | Really terrible weather for this project
351 | 42 mins | 15 | 180 | 16 | 7.36 | Enphase | Roof Mount | Yes | Yes | Truss | No | No | B2 | 68 | 47.4 | 50 | 1 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Winter | 57:45 | 2 | 5 | 0 | 0:00 | 57:45 | 5
352 | 26 mins | 30.3 | 158 | 14 | 5.6 | Enphase | Roof Mount | Yes | Yes | Truss | No | No | A1 | 74.8 | 40.9 | 48 | 2 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 2 | Winter | 43:00 | 1 | 5 | 0 | 0:00 | 43:00 | 5
353 | 51 mins | 39 | 163/250/70 | 26 | 11.7 | Enphase | Roof Mount | Yes | Yes | Truss | No | No | A4 | 68 | 47.4 | 50 | 4 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 3 | Winter | 98:00 | 2 | 5 | 0 | 0:00 | 98:00 | 5
354 | 7 mins |  |  | 8 | 3.68 | Enphase | Roof Mount | Yes | No | Rafter | No | Yes | A* | 68 | 47.4 | 50 | 2 | 0 | Asphalt Shingles | Flashfoot 2 | Portrait | 1 | Winter | 37:45 | 1 | 5 | 0 | 0:00 | 37:45 | 5

## Technical Analysis (hidden)
Analysis of MSP Residential and Commercial Data
Year | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2025 Estimated Full Year Info Based on Data | 2025 Estimated Full Year of Info Based on Business Plan
# of Installs | 55 | 62 | 81 | 86 | 84 | 119 | #REF!
kW Installed | 480 | 650 | 670 | 828 | 947 | 1249 | #REF!
Install Revenue | 1400000 | 1675000 | 1810000 | 2339533 | 2668936 | 3266869 | #REF!
Est. CoGs | - | - | - | - | 1681254 | 2062602 | #REF!
Est. Margin $ | - | - | - | - | 984551 | 1221323 | #REF!
Estimated Direct Labor Costs |  |  |  |  | 185660 | 267683 | #REF!
Estimated EC Cost | - | - | - | - | 154200 | 204936 | #REF!
Actual EC Cost | - | - | - | - | 113558 | 85130 | #REF!
Average System Price | - | - | 22353 | 27203 | 31773 | 27685 | #DIV/0!
Median System Price |  | - | 19206 | 24305 | 26342 | 21978 | #REF!
Average kW/Install | - | - | 8.3 | 8.76 | 11.28 | 10.5 | #REF!
Median kW/Install | - | - | 6.6 | 7.79 | 8.3 | 7.82 | #REF!
Average $/W | 2.93 | 2.61 | 2.7 | 2.83 | 2.82 | 2.62 | #REF!
Median $/W | - | - | 2.84 | 2.98 | 3.01 | 2.83 | #REF!
# of People | 5 | 8 | 9 | 10 | 12 | 14 | 15
Utility Breakdown - Count
MGE | - | - | 40 | 28 | 24 | 46 | #REF!
Alliant | - | - | 23 | 50 | 46 | 55 | #REF!
WE Energies | - | - | 6 | 1 | 2 | 2 | #REF!
Other | - | - | 10 | 7 | 12 | 10 | #REF!
Utility Breakdown - Percent
MGE | - | - | 49.38% | 32.56% | 28.6% | 36.5% | #VALUE!
Alliant | - | - | 28.4% | 58.14% | 54.8% | 43.7% | #VALUE!
WE Energies | - | - | 7.407% | 1.163% | 2.4% | 1.6% | #VALUE!
Other | - | - | 12.35% | 8.14% | 14.3% | 7.9% | #REF!
Inverter Manufacturer - Count
Enphase | - | - | 37 | 43 | 63 | 106 | #VALUE!
SolarEdge | - | - | 41 | 41 | 16 | 5 | #VALUE!
SMA | - | - | 2 | 2 | 4 | 1 | #VALUE!
Other | - | - | 1 | 0 | 1 | 4 | #VALUE!
Inverter Manufacturer - Percent
Enphase | - | - | 45.68% | 50% | 75% | 84.1% | #VALUE!
SolarEdge | - | - | 50.62% | 47.67% | 19% | 4% | #VALUE!
SMA | - | - | 2.469% | 2.326% | 4.8% | 0.8% | #VALUE!
Other | - | - | 1.235% | 0% | 1.2% | 3.2% | #VALUE!
Panel Manufacturer - Count
REC | - | - | 19 | 30 | 51 | 98 | #REF!
Silfab | - | - | 32 | 19 | 4 | 0 | #REF!
Aptos Solar | - | - | 0 | 12 | 0 | 0 | #REF!
Q-Cell | - | - | 10 | 9 | 8 | 3 | #REF!
Phono Solar | - | - | 3 | 9 | 1 | 0 | #REF!
Trina Solar | - | - | 3 | 2 | 15 | 6 | #REF!
Other | - | - | 14 | 5 | 5 | 12 | #REF!
Panel Manufacturer - Percentage
REC | - | - | 23.46% | 34.88% | 60.7% | 77.8% | #VALUE!
Silfab | - | - | 39.51% | 22.09% | 4.8% | 0% | #VALUE!
Aptos Solar | - | - | 0% | 13.95% | 0% | 0% | #VALUE!
Q-Cell | - | - | 12.35% | 10.47% | 9.5% | 2.4% | #VALUE!
Phono Solar | - | - | 3.704% | 10.47% | 1.2% | 0% | #VALUE!
Trina Solar | - | - | 3.704% | 2.326% | 17.9% | 4.8% | #VALUE!
Other | - | - | 17.28% | 5.814% | 6% | 9.5% | #REF!
System Size (kW)
0-2 | - | - | 1 | 1 | 1 | 0 | #VALUE!
2023-02-04 | - | - | 5 | 6 | 5 | 7 | #VALUE!
2023-04-06 | - | - | 29 | 16 | 12 | 31 | #VALUE!
2023-06-08 | - | - | 21 | 21 | 19 | 25 | #VALUE!
2023-08-10 | - | - | 5 | 21 | 16 | 17 | #VALUE!
2022-10-12 | - | - | 7 | 9 | 12 | 16 | #VALUE!
2022-12-15 | - | - | 4 | 3 | 7 | 8 | #VALUE!
15-20 | - | - | 5 | 4 | 5 | 9 | #VALUE!
20-50 | - | - | 4 | 4 | 5 | 4 | #VALUE!
>50 | - | - | 0 | 1 | 2 | 2 | #VALUE!
System Size - Percentage
0-2 | - | - | 1.235% | 1.163% | 1.2% | 0% | #VALUE!
2023-02-04 | - | - | 6.173% | 6.977% | 6% | 5.6% | #VALUE!
2023-04-06 | - | - | 35.8% | 18.6% | 14.3% | 24.6% | #VALUE!
2023-06-08 | - | - | 25.93% | 24.42% | 22.6% | 19.8% | #VALUE!
2023-08-10 | - | - | 6.173% | 24.42% | 19% | 13.5% | #VALUE!
2022-10-12 | - | - | 8.642% | 10.47% | 14.3% | 12.7% | #VALUE!
2022-12-15 | - | - | 4.938% | 3.488% | 8.3% | 6.3% | #VALUE!
15-20 | - | - | 6.173% | 4.651% | 6% | 7.1% | #VALUE!
20-50 | - | - | 4.938% | 4.651% | 6% | 3.2% | #VALUE!
>50 | - | - | 0% | 1.163% | 2.4% | 1.6% | #VALUE!
Contract Value - Count
$0 - $10,000 | - | - | 1 | 2 | 1 | 0 | #REF!
$10,001 - $15,000 | - | - | 18 | 7 | 10 | 29 | #REF!
$15,001 - $20,000 | - | - | 25 | 16 | 6 | 18 | #REF!
$20,001 - $25,000 | - | - | 18 | 24 | 22 | 25 | #REF!
$25,001 - $30,000 | - | - | 4 | 18 | 21 | 20 | #REF!
$30,001 - $35,000 | - | - | 7 | 7 | 7 | 5 | #REF!
$35,001 - $40,000 | - | - | 2 | 2 | 3 | 9 | #REF!
$40,001 - $45,000 | - | - | 2 | 4 | 5 | 4 | #REF!
$45,001 - $50,000 | - | - | 2 | 2 | 0 | 1 | #REF!
Above $50,000 | - | - | 2 | 4 | 9 | 7 | #REF!
Contract Value - Percent
$0 - $10,000 | - | - | 1.235% | 2.326% | 1.2% | 0% | #REF!
$10,001 - $15,000 | - | - | 22.22% | 8.14% | 11.9% | 23% | #REF!
$15,001 - $20,000 | - | - | 30.86% | 18.6% | 7.1% | 14.3% | #REF!
$20,001 - $25,000 | - | - | 22.22% | 27.91% | 26.2% | 19.8% | #REF!
$25,001 - $30,000 | - | - | 4.938% | 20.93% | 25% | 15.9% | #REF!
$30,001 - $35,000 | - | - | 8.642% | 8.14% | 8.3% | 4% | #REF!
$35,001 - $40,000 | - | - | 2.469% | 2.326% | 3.6% | 7.1% | #REF!
$40,001 - $45,000 | - | - | 2.469% | 4.651% | 6% | 3.2% | #REF!
$45,001 - $50,000 | - | - | 2.469% | 2.326% | 0% | 0.8% | #REF!
Above $50,000 | - | - | 2.469% | 4.651% | 10.7% | 5.6% | #REF!
Interconnection Type - Count
A1 | - | - | - | 42 | 46 | 76 | #VALUE!
A2 | - | - | - | 11 | 4 | 3 | #VALUE!
A3 | - | - | - | 6 | 2 | 6 | #VALUE!
A4 | - | - | - | 3 | 8 | 10 | #VALUE!
A* | - | - | - | 5 | 8 | 2 | #VALUE!
B1 | - | - | - | 7 | 4 | 1 | #VALUE!
B2 | - | - | - | 3 | 3 | 2 | #VALUE!
B* | - | - | - | 0 | 1 | 1 | #VALUE!
C1 | - | - | - | 1 | 2 | 6 | #VALUE!
C2 | - | - | - | 1 | 0 | 3 | #VALUE!
C3 | - | - | - | 4 | 3 | 4 | #VALUE!
C* | - | - | - | 4 | 3 | 1 | #VALUE!
QTY by Job Type
Residential | - | - | - | 83 | 79 | 113 | #REF!
Commercial | - | - | - | 3 | 5 | 6 | #VALUE!
Roof Mount | - | - | - | 81 | 76 | 117
Ground Mount | - | - | - | 5 | 8 | 2
Revenue by Job Type
Residential | - | - | - | 2066477 | 2126036 | 2726891 | #REF!
Commercial | - | - | - | 273056 | 542900 | 539978 | #REF!
Roof Mount | - | - | - | 2049476 | 2356326 | 3023168
Ground Mount | - | - | - | 290057 | 312610 | 61937
Margin by Job Type
Residential | - | - | - | - | 776157 | 1030055 | #REF!
Commercial | - | - | - | - | 208393 | 191268 | #REF!
Roof Mount | - | - | - | - | 869801 | 1144304
Ground Mount | - | - | - | - | 114750 | 24775
Estimated Direct Labor by Job Type
Residential | [5 empty] | 232323 | #REF!
Commercial | [5 empty] | 35360 | #REF!
Roof Mount | [5 empty] | 251515
Ground Mount | [5 empty] | 4888
kW by Job Type
Residential | - | - | - | 696 | 709 | 981 | #REF!
Commercial | - | - | - | 133 | 238 | 269 | #REF!
Roof Mount | - | - | - | 707 | 844 | 1157
Ground Mount | - | - | - | 122 | 104 | 21
Average kW by Job Type
Residential | - | - | - | 8.3855 | 9 | 8.6 | #REF!
Commercial | - | - | - | 44.3333 | 47.6 | 44.8 | #REF!
Roof Mount | - | - | - | 8.7284 | 11.1 | 9.9
Ground Mount | - | - | - | 24.4 | 12.9 | 10.7
Average Revenue by Job Type
Residential | - | - | - | 24897.3133 | 26912 | 23920 | #REF!
Commercial | - | - | - | 91018.6667 | 108580 | 89996 | #REF!
Roof Mount | - | - | - | 25302.1728 | 31004 | 25839
Ground Mount | - | - | - | 58011.4 | 39076 | 30969
Average Margin by Job Type
Residential | - | - | - | - | 9825 | 9036 | #REF!
Commercial | - | - | - | - | 41679 | 31878 | #REF!
Roof Mount | - | - | - | - | 11445 | 9780
Ground Mount | - | - | - | - | 14344 | 12388
Average Margin + Labor by Job Type
Residential | [5 empty] | 11073 | #REF!
Commercial | [5 empty] | 37771 | #REF!
Roof Mount | [5 empty] | 11930
Ground Mount | [5 empty] | 14832
QTY by Job Category
Category 1 | - | - | - | 47 | 40 | 69
Category 2 | - | - | - | 24 | 22 | 25
Category 3 | - | - | - | 15 | 22 | 21
Revenue by Job Category
Category 1 | - | - | - | 1068817 | 992361 | 1383584
Category 2 | - | - | - | 553116 | 502304 | 583634
Category 3 | - | - | - | 717600 | 1174271 | 899146
Margin by Job Category
Category 1 | - | - | - | - | 360298 | 538303
Category 2 | - | - | - | - | 185463 | 216995
Category 3 | - | - | - | - | 438790 | 335354
kW by Job Category
Category 1 | - | - | - | 362 | 346 | 507
Category 2 | - | - | - | 175 | 158 | 210
Category 3 | - | - | - | 291 | 444 | 336
Average kW by Job Category
Category 1 | - | - | - | 7.7021 | 8.7 | 7.3
Category 2 | - | - | - | 7.2917 | 7.2 | 8.4
Category 3 | - | - | - | 19.4 | 20.2 | 16
Average Revenue by Job Category
Category 1 | - | - | - | 22740.7872 | 24809 | 20052
Category 2 | - | - | - | 23046.5 | 22832 | 23345
Category 3 | - | - | - | 47840 | 53376 | 42816
Average Margin by Job Category
Category 1 | - | - | - | - | 9007 | 7801
Category 2 | - | - | - | - | 8430 | 8680
Category 3 | - | - | - | - | 19945 | 15969
Truss Install QTY |  |  | 55 | 62 | 53 | 83 | #VALUE!
Rafter or Purlin Install QTY |  |  | 22 | 17 | 20 | 27 | #VALUE!
Reinforcement Install QTY |  |  | 11 | 5 | 11 | 17 | #VALUE!
Percent of installs that are Truss |  |  | 67.9% | 72.09% | 63.1% | 65.87% | #VALUE!
Percent of installs that are Rafter or Purlin |  |  | 27.16% | 19.77% | 23.8% | 21.43% | #VALUE!
Percent of Rafter installs needing reinforcement |  |  | 50% | 29.41% | 55% | 62.96% | #VALUE!
Percent of total installs needing reinforcement |  |  | 13.58% | 5.81% | 13.1% | 13.49% | #VALUE!
% Projects in City of Madison |  |  | 35.8% | 40.7% | 26.19% | 51.35% | #REF!

## CORE METRICS + (hidden)
OVERALL - RESIDENTIAL + COMMERCIAL
[6 empty] | Budgetted Bookings |  |  | Actual Bookings (non service) |  |  | Permits |  |  |  |  | Utility Applications |  |  |  |  | Budgetted Install Schedule |  |  | Planned Installs at Contract Signing (non service) |  |  | Actual Installations (non service) |  |  | Budgeted Bookings vs Actual Bookings |  |  | Budgeted Installs vs Actual Installs |  |  | Planned Installs at Contract vs Actual Install
|  |  |  | Month | Derived Booking Value percentage per Month | QTY Booked | kW Booked | Contract Value of Booked Systems | QTY Booked | kW Booked | Contract Value of Booked Systems | Permits Submitted | Permits Approved | Jobs with Unsubmitted Permits | Outstanding Submitted Permits MTD or at Months End | Total Approved But Uninstalled Permits MTD or at Month End | Utility Applications Submitted | Utility Applications Approved | Jobs with Unsubmitted Utility Applications | Outstanding Submitted Utility Applications MTD or at Months End | Total Approved but Uninstalled Utility Applications MTD or at Months End | QTY Installed | kW Installed | Contract Value of Installed Systems | QTY Installed | kW Installed | Contract Value of Installed Systems | QTY Installed | kW Installed | Contract Value of Installed Systems | QTY Booked | kW Booked | Contract Value of Booked Systems | QTY Installed | kW Installed | Contract Value of Installed Systems | QTY Installed | kW Installed | Contract Value of Installed Systems
>=1/1/23 | <1/1/24 | 0 | >=1/1/24 | 2023 | N/A |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF! | 0 | #REF! |  |  |  | #REF! | #REF! | #REF! | [9 empty] | #REF! | #REF! | #REF!
>=1/1/24 | <2/1/24 | 1 | >=2/1/24 | January | 6.03% | 6 | 101.6592 | 211050 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF! | 0 | #REF! | 4 | 40 | 111072.4194 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
>=2/1/24 | <3/1/24 | 2 | >=3/1/24 | February | 5.47% | 6 | 94.6005 | 191450 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | 2 | 20 | 55536.2097 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
>=3/1/24 | <4/1/24 | 3 | >=4/1/24 | March | 8.04% | 9 | 126.9949 | 281400 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | 7 | 113.5 | 238422.6934 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
>=4/1/24 | <5/1/24 | 4 | >=5/1/24 | April | 10.18% | 11 | 153.9692 | 356300 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | 11 | 153.5 | 349495.1129 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
>=5/1/24 | <6/1/24 | 5 | >=6/1/24 | May | 10.68% | 12 | 160.2716 | 373800 | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! |  |  |  | 11 | 153.5 | 349495.1129 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
>=6/1/24 | <7/1/24 | 6 | >=7/1/24 | June | 10.37% | 12 | 156.3641 | 362950 | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! |  |  |  | 11 | 153.5 | 349495.1129 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
>=7/1/24 | <8/1/24 | 7 | >=8/1/24 | July | 6.41% | 7 | 106.449 | 224350 | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! |  |  |  | 12 | 163.5 | 377263.2177 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
>=8/1/24 | <9/1/24 | 8 | >=9/1/24 | August | 9.33% | 10 | 143.2551 | 326550 | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! |  |  |  | 12 | 163.5 | 377263.2177 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
>=9/1/24 | <10/1/24 | 9 | >=10/1/24 | September | 8.29% | 9 | 130.1461 | 290150 | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! |  |  |  | 11 | 153.5 | 349495.1129 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
>=10/1/24 | <11/1/24 | 10 | >=11/1/24 | October | 10.56% | 13 | 133.107 | 369600 | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! |  |  |  | 12 | 163.5 | 377263.2177 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
>=11/1/24 | <12/1/24 | 11 | >=12/1/24 | November | 6.53% | 8 | 82.3095 | 228550 | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! |  |  |  | 9 | 90 | 249912.9437 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
>=12/1/24 | <1/1/25 | 12 | >=1/1/25 | December | 8.11% | 10 | 102.2252 | 283850 | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! |  |  |  | 6 | 60 | 166608.6291 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
>=1/1/25 | <1/1/26 |  | >=1/1/26 | 2025 | N/A |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | [6 empty] | #REF! | #REF! | #REF!
|  |  |  | Total | 100% | 112.7913 | 1491.3513 | 3500000 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | 108 | 1428 | 3351323 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  |  | Total* | 100% |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | [6 empty] | #REF! | #REF! | #REF! | [9 empty] | #REF! | #REF! | #REF!
*Removes 2023 and 2025 data
[10 empty] | June - September is all resi | [11 empty] | 1000 kW Resi | [8 empty] | Positive Numbers Indicate we are ahead of schedule in terms of actual bookings |  |  | Positive Numbers Indicate we are ahead of schedule in terms of actual installations |  |  | Positive Numbers Indicate we are ahead of schedule in terms of actual installations vs what we planned on doing at contract signing (BD Actuals)
[6 empty] | $3,500,000 in bookings is the target | [15 empty] | 428 kW Commercial
[6 empty] | Since booking revenue target is 4.44% greater than installed revenue target, kW booked and QTY booked targets are taken to be 1.0444* Install Goals for 2024 | [15 empty] | 108 Jobs Total
No plan as to which months the commercial projects will land in
Yearly Avg kW target: 13.23kW/system (blend of resi + commercial)
Yearly Avg kW target: 13.23kW/system (blend of resi + commercial)
[31 empty] | Bookings |  |  | Installs
|  |  |  | Month | [25 empty] | # of Months Left | Average monthly residential + commercial bookings needed to be in line with Budgeted Goals |  |  | Average monthly residential + commercial installs needed to be in line with Budgeted Goals
|  |  |  | January | [25 empty] | 12
|  |  |  | February | [25 empty] | 11
|  |  |  | March | [25 empty] | 10
|  |  |  | April | [25 empty] | 9 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  |  | May | [25 empty] | 8
|  |  |  | June | [25 empty] | 7
|  |  |  | July | [25 empty] | 6
|  |  |  | August | [25 empty] | 5
|  |  |  | September | [25 empty] | 4
|  |  |  | October | [25 empty] | 3
|  |  |  | November | [25 empty] | 2
|  |  |  | December | [25 empty] | 1
|  |  |  | Total | [26 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
RESIDENTIAL
[6 empty] | Budgetted Bookings |  |  | Actual Bookings |  |  | Permits |  |  |  |  | Utility Applications |  |  |  |  | Budgetted Install Schedule |  |  | Planned Installs at Contract Signing |  |  | Actual Installations |  |  | Budgeted Bookings vs Actual Bookings |  |  | Budgeted Installs vs Actual Installs |  |  | Planned Installs at Contract vs Actual Install
|  |  |  | Month | Median Booking %/month 2021-2023 average | QTY Booked | kW Booked | Contract Value of Booked Systems | QTY Booked | kW Booked | Contract Value of Booked Systems | Permits Submitted | Permits Approved | Jobs with Unsubmitted Permits | Outstanding Submitted Permits MTD or at Months End | Total Approved But Uninstalled Permits MTD or at Month End | Utility Applications Submitted | Utility Applications Approved | Jobs with Unsubmitted Utility Applications | Outstanding Submitted Utility Applications MTD or at Months End | Total Approved but Uninstalled Utility Applications MTD or at Months End | QTY Installed | kW Installed | Contract Value of Installed Systems | QTY Installed | kW Installed | Contract Value of Installed Systems | QTY Installed | kW Installed | Contract Value of Installed Systems | QTY Booked | kW Booked | Contract Value of Booked Systems | QTY Installed | kW Installed | Contract Value of Installed Systems | QTY Installed | kW Installed | Contract Value of Installed Systems
>=1/1/23 | <1/1/24 | 0 | >=1/1/24 | 2023 | N/A |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF! | 0 | #REF! |  |  |  | #REF! | #REF! | #REF! | [9 empty] | 0 | 0 | 0
>=1/1/24 | <2/1/24 | 1 | >=2/1/24 | January | 6.22% | 5 | 51.9979 | 144383.3333 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF! | 0 | #REF! | 4 | 40 | 111072.4194 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
>=2/1/24 | <3/1/24 | 2 | >=3/1/24 | February | 6.64% | 5 | 44.9392 | 124783.3333 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | 2 | 20 | 55536.2097 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
>=3/1/24 | <4/1/24 | 3 | >=4/1/24 | March | 7.05% | 8 | 77.3336 | 214733.3333 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | 6 | 60 | 166608.6291 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
>=4/1/24 | <5/1/24 | 4 | >=5/1/24 | April | 12.86% | 10 | 104.3079 | 289633.3333 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | 10 | 100 | 277681.0486 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
>=5/1/24 | <6/1/24 | 5 | >=6/1/24 | May | 13.28% | 11 | 110.6104 | 307133.3333 | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! |  |  |  | 10 | 100 | 277681.0486 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
>=6/1/24 | <7/1/24 | 6 | >=7/1/24 | June | 7.88% | 11 | 106.7029 | 296283.3333 | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! |  |  |  | 10 | 100 | 277681.0486 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
>=7/1/24 | <8/1/24 | 7 | >=8/1/24 | July | 9.96% | 6 | 56.7877 | 157683.3333 | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! |  |  |  | 11 | 110 | 305449.1534 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
>=8/1/24 | <9/1/24 | 8 | >=9/1/24 | August | 4.56% | 9 | 93.5938 | 259883.3333 | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! |  |  |  | 11 | 110 | 305449.1534 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
>=9/1/24 | <10/1/24 | 9 | >=10/1/24 | September | 5.81% | 8 | 80.4848 | 223483.3333 | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! |  |  |  | 10 | 100 | 277681.0486 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
>=10/1/24 | <11/1/24 | 10 | >=11/1/24 | October | 9.96% | 13 | 133.107 | 369600 | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! |  |  |  | 11 | 110 | 305449.1534 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
>=11/1/24 | <12/1/24 | 11 | >=12/1/24 | November | 9.54% | 8 | 82.3095 | 228550 | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! |  |  |  | 9 | 90 | 249912.9437 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
>=12/1/24 | <1/1/25 | 12 | >=1/1/25 | December | 6.22% | 10 | 102.2252 | 283850 | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! |  |  |  | 6 | 60 | 166608.6291 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
>=1/1/25 | <1/1/26 |  | >=1/1/26 | 2025 | N/A |  |  |  | #REF! | #REF! | #REF! | [5 empty] | #REF! | #REF! | [6 empty] | #REF! | #REF! | #REF!
|  |  |  | Total | N/A | 104.44 | 1044.4 | 2900000 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | 100 | 1000 | 2776810.4857 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  |  | Total* | N/A |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! |  |  |  | 100 | 1000 | 2776810.4857 | #REF! | #REF! | #REF! | [9 empty] | #REF! | #REF! | #REF!
2450980
[31 empty] | Bookings |  |  | Installs
|  |  |  | Month | [25 empty] | # of Months Left | Average monthly residential bookings needed to be in line with Budgeted Goals |  |  | Average monthly residential installs needed to be in line with Budgeted Goals
|  |  |  | January | [25 empty] | 12
|  |  |  | February | [25 empty] | 11
|  |  |  | March | [25 empty] | 10
|  |  |  | April | [25 empty] | 9 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  |  | May | [25 empty] | 8
|  |  |  | June | [25 empty] | 7
|  |  |  | July | [25 empty] | 6
|  |  |  | August | [25 empty] | 5
|  |  |  | September | [25 empty] | 4
|  |  |  | October | [25 empty] | 3
|  |  |  | November | [25 empty] | 2
|  |  |  | December | [25 empty] | 1
|  |  |  | Total | [26 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
COMMERCIAL
[6 empty] | Budgetted Bookings |  |  | Actual Bookings |  |  | Permits |  |  |  |  | Utility Applications |  |  |  |  | Budgetted Install Schedule |  |  | Planned Installs at Contract Signing |  |  | Actual Installations |  |  | Budgeted Bookings vs Actual Bookings |  |  | Budgeted Installs vs Actual Installs |  |  | Planned Installs at Contract vs Actual Install
|  |  |  | Month | 2023 % of Bookings Per Month | QTY Booked | kW Booked | Contract Value of Booked Systems | QTY Booked | kW Booked | Contract Value of Booked Systems | Permits Submitted | Permits Approved | Jobs with Unsubmitted Permits | Outstanding Submitted Permits MTD or at Months End | Total Approved But Uninstalled Permits MTD or at Month End | Utility Applications Submitted | Utility Applications Approved | Jobs with Unsubmitted Utility Applications | Outstanding Submitted Utility Applications MTD or at Months End | Total Approved but Uninstalled Utility Applications MTD or at Months End | QTY Installed | kW Installed | Contract Value of Installed Systems | QTY Installed | kW Installed | Contract Value of Installed Systems | QTY Installed | kW Installed | Contract Value of Installed Systems | QTY Booked | kW Booked | Contract Value of Booked Systems | QTY Installed | kW Installed | Contract Value of Installed Systems | QTY Installed | kW Installed | Contract Value of Installed Systems
>=1/1/23 | <1/1/24 | 0 | >=1/1/24 | 2023 | N/A |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF! | 0 | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [6 empty] | #REF! | #REF! | #REF!
>=1/1/24 | <2/1/24 | 1 | >=2/1/24 | January | N/A | 1 | 49.6613 | 66666.6667 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | #REF! | #REF! | #REF! | #REF! | 0 | #REF! | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
>=2/1/24 | <3/1/24 | 2 | >=3/1/24 | February | N/A | 1 | 49.6613 | 66666.6667 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
>=3/1/24 | <4/1/24 | 3 | >=4/1/24 | March | N/A | 1 | 49.6613 | 66666.6667 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | 1 | 53.5 | 71814.0643 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
>=4/1/24 | <5/1/24 | 4 | >=5/1/24 | April | N/A | 1 | 49.6613 | 66666.6667 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | 1 | 53.5 | 71814.0643 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
>=5/1/24 | <6/1/24 | 5 | >=6/1/24 | May | N/A | 1 | 49.6613 | 66666.6667 | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! |  |  |  | 1 | 53.5 | 71814.0643 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
>=6/1/24 | <7/1/24 | 6 | >=7/1/24 | June | N/A | 1 | 49.6613 | 66666.6667 | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! |  |  |  | 1 | 53.5 | 71814.0643 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
>=7/1/24 | <8/1/24 | 7 | >=8/1/24 | July | N/A | 1 | 49.6613 | 66666.6667 | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! |  |  |  | 1 | 53.5 | 71814.0643 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
>=8/1/24 | <9/1/24 | 8 | >=9/1/24 | August | N/A | 1 | 49.6613 | 66666.6667 | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! |  |  |  | 1 | 53.5 | 71814.0643 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
>=9/1/24 | <10/1/24 | 9 | >=10/1/24 | September | N/A | 1 | 49.6613 | 66666.6667 | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! |  |  |  | 1 | 53.5 | 71814.0643 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
>=10/1/24 | <11/1/24 | 10 | >=11/1/24 | October | N/A | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! |  |  |  | 1 | 53.5 | 71814.0643 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
>=11/1/24 | <12/1/24 | 11 | >=12/1/24 | November | N/A | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! |  |  |  | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
>=12/1/24 | <1/1/25 | 12 | >=1/1/25 | December | N/A | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! |  |  |  | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
>=1/1/25 | <1/1/26 |  | >=1/1/26 | 2025 | N/A |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | [6 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  |  | Total | N/A | 9 | 446.9513 | 600000 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! |  | #REF! | 8 | 428 | 574512.5143 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  |  | Total* | N/A |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! |  |  |  | 8 | 428 | 574512.5143 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[31 empty] | Bookings |  |  | Installs
|  |  |  | Month | [25 empty] | # of Months Left | Average monthly commercial bookings needed to be in line with Budgeted Goals |  |  | Average monthly residential installs needed to be in line with Budgeted Goals
|  |  |  | January | [25 empty] | 12
|  |  |  | February | [25 empty] | 11
|  |  |  | March | [25 empty] | 10
|  |  |  | April | [25 empty] | 9 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  |  | May | [25 empty] | 8
|  |  |  | June | [25 empty] | 7
|  |  |  | July | [25 empty] | 6
|  |  |  | August | [25 empty] | 5
|  |  |  | September | [25 empty] | 4
|  |  |  | October | [25 empty] | 3
|  |  |  | November | [25 empty] | 2
|  |  |  | December | [25 empty] | 1
|  |  |  | Total | [26 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Formulas:
Jobs with Unsubmitted Permits = INDEX(P5:[Jobs with Unsubmitted Permits, row above],MONTH(TODAY())+1)
QTY Installed = IF(MONTH(TODAY())>=D5,[Actual Installations (non service)]-[QTY Installed],"")
QTY Installed = IF(MONTH(TODAY())>=D5,[Actual Installations (non service)]-[Budgetted Install Schedule],"")
Budgeted Bookings vs Actual Bookings = IF(MONTH(TODAY())>=D6,[Actual Bookings (non service)]-[Budgetted Bookings],"")
Budgeted Bookings vs Actual Bookings = IF(MONTH(TODAY())=D6,AH47/[Contract Value of Installed Systems],"")
Budgeted Installs vs Actual Installs = IF(MONTH(TODAY())>=D6,[Actual Installations (non service)]-[Budgetted Install Schedule],"")
Budgeted Installs vs Actual Installs = IF(MONTH(TODAY())=D6,AL47/[Contract Value of Installed Systems],"")
kW Booked = IF(MONTH(TODAY())=D6,AI47/[Contract Value of Installed Systems],"")
Contract Value of Booked Systems = IF(MONTH(TODAY())=D6,AJ47/[Contract Value of Installed Systems],"")
kW Installed = IF(MONTH(TODAY())=D6,AM47/[Contract Value of Installed Systems],"")
Contract Value of Installed Systems = IF(MONTH(TODAY())=D6,AN47/[Contract Value of Installed Systems],"")

## DTS Dashboard (hidden)
DTS Dashboard
Item | Month to Date Actual vs End of Month Target |  |  |  | Year To Date
| Full MonthTarget | Actual | Target to Actual QTY | Target to Actual % | Target for the end of the month | Actual | Target to Actual QTY | Target to Actual %
QTY Installed | 11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
kW Install | 153.5 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Revenue $ Installed | 349495.1129 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Permits Submitted |  | #REF! |  |  |  | #REF!
Permits Approved |  | #REF! |  |  |  | #REF!
Jobs with Unsubmitted Permits | [5 empty] | #REF!
Outstanding Submitted Permits
Total Approved Permits for Uninstalled Projects | [5 empty] | #REF!
Utility Applications Submitted |  | #REF! |  |  |  | #REF!
Utility Applications Approved |  | #REF! |  |  |  | #REF!
Jobs with Unsubmitted Utility Applications | [5 empty] | #REF!
Outstanding Submitted Utility Applications
Total Approved Utility Applications for Uninstalled Projects | [5 empty] | #REF!
QTY of Projects that have Full Approval to Move Forward Now | [5 empty] | #REF!
QTY of Projects that do not have Full Approval to move forward now | [5 empty] | #REF!
QTY of Installed projects without PTO | [5 empty] | #REF!
Next Project on Calendar without full approval | [5 empty] | Crabb
Days until that project | [5 empty] | #NUM!
Next Project on Calendar that we haven't submitted everything for | [5 empty] | Binsfeld
Days until that project | [5 empty] | #NUM!
Permitted Project Lead Time (weeks) |  |  |  |  | 8 | #NUM!
QTY of New Warranty Calls |  | #REF! |  |  |  | #REF!
QTY of Warranty Items Open